## Weekly Status (hidden)
| 2018-12-09 | 2018-12-16 | 2018-12-23 | 2018-12-30 | 2018-01-03 | 2018-01-10 | 2018-01-24 | 2018-02-07 | 2018-02-14 | 2018-02-23 | 2018-02-28 | 2018-03-07 | 2018-03-14 | 2018-03-21 | 2018-03-28 | 2018-04-04 | 2018-04-11 | 2018-04-18 | 2018-05-02 | 2018-05-09 | 2018-05-16 | 2018-05-30 | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | 2018-07-04 | 2018-07-11 | 2018-07-18 | 2018-07-25 | 2018-08-01 | 2018-08-08 | 2018-08-15 | 2018-08-22 | 2018-08-30 | 2018-09-06 | 2018-09-13 | 2018-09-20 | 2018-10-01 | 2018-10-11 | 2018-10-17 | 2018-10-24 | 2018-10-31 | 2018-11-07
Media |  | Marketing campaigns | Marketing campaigns |  |  | Pixels setup on Partner end | Pixels setup on Envyus/PeopleFinder / Spokeo | Pixels setup on Spokeo | Pixels setup on Spokeo | Adwords optimization |  | review lessons learned from google TV campaign (for PR) | review lessons learned from google TV campaign (for PR) | review lessons learned from google TV campaign (for PR) | sales site changes for campaigns (MC) | sales site changes for campaigns (MC) | image -> UXC Set mapping |  | remarketing (MC) | Better traffic quality (search rate) | [5 empty] | Broad Modified test and Broad test | End broad test | Envyus payment? | Background Check, Public Record, competitors campaigns (new way to start) | Background Check, Public Record, Phone, competitors campaigns (new way to start) | Background Check, Public Record, Phone (new way to start) | Background Check, Public Record, Phone (new way to start) | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status | new campaigns - Background, Public, Compet status. Provide skelton info | new campaigns - Background, Public, Compet status. Provide skelton info | new campaigns - Background, Public, Compet status. Provide skelton info
[20 empty] | Remkt (email) |  |  | Remarketing analysis - # of days since EO Capture; retention | Remarketing analysis - # of days since EO Capture; retention |  |  |  | demographic analysis | Phone, Inmate, Sex Offender campaigns (spin off) | Inmate, Sex Offender campaigns (spin off) | SUP copy for different campaigns |  | problem campaigns - update Monday (see DAR comment) | problem campaigns - update Monday (see DAR comment) | pull retention data by adgroup ID (since UXC data does not appear consistent) | pull retention data by adgroup ID (since UXC data does not appear consistent) |  |  |  |  | slowly increase Inmate
| Send email to product. need # of UXC, special config needed (headlines?), variables to store needed and product will send back full url | write short copy for C | write short copy for C | <-- done | Urls for Spokeo | Urls for PeopleFInder/BeenVerified | affiliate id for PF |  | Hard to do tests if CR is so low. Switch search to SV? 0.38% -> 1.07% CR? | set up goals for Search | set up goals for Search | why is google disapproved our ads; optimize mobile campaign | google restarted on saturday | figure out what campaigns need to be setup and get UXC setup for it | figure out what campaigns need to be setup and get UXC setup for it | figure out what campaigns need to be setup and get UXC setup for it | try gray images of faces |  | retargeting (LC) | Figure out other categories (people search, public records) |  |  |  | increase TV budget to compare vs. spyfly, and since PR is break even |  |  | comments strategy | comments strategy |  | check extensions for all adgroups/campaigns | competitor campaigns - no copy customization yet (uses People Search copy) | competitor campaigns - no copy customization yet (uses People Search copy) |  | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM is a sponsored link... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM is a sponsored link... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links... | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links... |  |  | Pipl 3rd party sponsored links. API returns sponsored links for other data consumers to use. ICM and BV are sponsored links...
| Applied for EnvyUS campaigns, waiting on response |  |  |  |  | Anything interesting from LV? | Url for PeopleFinder / Spokeo | Url for Spokeo | Url for Spokeo |  | go visit Spokeo | go visit Spokeo | go visit Spokeo | go visit Spokeo | go visit Spokeo | go visit Spokeo |  |  | push notification (LC) | Facebook |  |  |  | Increase CM budget to see if test #1 and #2 $1 is working |  |  | 2nd adwords account | analyze keywords that were re-added "free", "phone", etc | "criminal background" adgroup / campaign | "criminal background" adgroup / campaign | check extensions for all adgroups/campaigns |  | device type analysis | device type analysis | device type analysis | device type analysis |  | device type analysis | device type analysis | device type analysis |  | device type analysis
| Writing copy for mobile A-C | [7 empty] | Annotate notes into GA so you can see how it impacts CR | Notes plan = GA, DAR/Adwords | test bing | decide on PR conversion points | decide on PR conversion points |  | www.onesignal.com | www.onesignal.com | ask google about structure for 200M unique names "mark Chin" | ask google about structure for 200M unique names "mark Chin" | casX (MC) | google contact |  |  |  | Add in 1M names to Nationwide and stop CA campaigns | review negative keywords (outside Standard) | review negative keywords (outside Standard) |  | review negative keywords (outside Standard) | $1 ads vs. no $1 ads | $1 ads vs. no $1 ads | demographic investigation | demographic investigation - need to consider LTV | demographic investigation - need to consider LTV utm_demo=25_35 (google term) | demographic investigation - need to consider LTV utm_demo=25_35 (google term) | tag everyone as utm_demo | tag everyone as utm_demo |  |  | Testing moving backwards in time to various changes to see if retention gets fixed (rollback, pricing, marketing, what order? and more importantly do they interact?) | testing backwards marketing->pricing->rollback
[11 empty] | clean up campaigns | start preparing PR campaign - selecting products to focus on; figure out how to get keyword into ad dynamically (people search for lionel chin) | start preparing PR campaign - selecting products to focus on | start preparing PR campaign - selecting products to focus on | start preparing PR campaign - selecting products to focus on | ask google - pixels and personal name keyword insertion |  |  | Adsense | [5 empty] | negative age group | negative age group |  | negative age group | changing automated campaign budgets, cpa targets | changing automated campaign budgets, cpa targets |  | server and CSR capacity constraints | server and CSR capacity constraints | server and CSR capacity constraints | pull google costs automatically via API so the DAR is automatic https://developers.google.com/adwords/api/docs/guides/start |  |  |  |  | add cpa target experiment (LocateX), add utm_demo parameters (utm_demo=cpa_30). Need to set UTM for all campaigns |  | pull google costs automatically via API so the DAR is automatic https://developers.google.com/adwords/api/docs/guides/start
| Will do banners when needed | [7 empty] | Confirm GA is main reporting tool |  | complete TV campaign for google adwords | test retargeting | test retargeting | test retargeting | starting with only search, waiting on display/retargeting/remarketing | sequence of marketing = google search, bing search, google display/remarketing, yahoo, envyus, facebook | copy changes for PR LP's | configure new LP images | try People and Public campaigns after site is "done" (1 week) | [7 empty] | automated bidding |  | conversion = S1% | conversion = S1% |  |  |  | Sales planning. Do we slow down sales where we will know LTV soon enough and increase sales where we want to find out? (assuming CPA is now known) | Sales planning. keep sales at 100 S0/day |  |  | add cpa target experiment (LocateX), add utm_demo parameters (utm_demo=cpa_30). Need to set UTM for all campaigns | add cpa target experiment (LocateX), add utm_demo parameters (utm_demo=cpa_30). Need to set UTM for all campaigns | check for display "pay for conversion" option
[15 empty] | sex offender data set - ask CSID | sex offender data set - ask CSID | Adsense - research | Adsense - research |  |  |  | mini conversion tracking? | mini conversion tracking? |  |  |  | attribution model |  | CPC change day to day | CPC change day to day | Remarketing for Inmate and Sex - which UXC's (3x versions) |  |  | Assuming some CSR coverage this weekend is set, ok to scale to 150 S0/day assuming no cash flow constraint |  | check for display "pay for conversion" option | check for display "pay for conversion" option | check for display "pay for conversion" option | check for display "pay for conversion" option | set up conversion tracking for 2 other google accounts - Secondary and Tertiary
Ops | [20 empty] | Verifi Dispute Questionaire | CB emails from Qualpay - send to gmail? 2 or 3 CB's? |  | 3DS qualpay | 3DS qualpay (nsoft+QP) | Get V/MC certs for 3DS | Get V/MC certs for 3DS | Get V/MC certs for 3DS | Get V cert for 3DS | tracking is not perfect. Compare emails vs. DAR |  |  | Hire CSR? |  | CSR Job Posting. stop posting | Chase newsletter re: 3DS? |  |  | Are CSRs all paid? | Interactive SUP Test plan |  | Interactive SUP Test plan
[21 empty] | CSR App access | how to exclude "bad" signups due to CSR and billing errors - 5/25 - 5/29 |  |  |  | Find a hourly CSR | Find CSR (send w3bstore the UX) | CSR Training and will start tomorrow | [6 empty] | Chromebook+mic for CSR? Is this supported? It is supported by freshcaller | discrepancy between adwords tracking and our d/b is growing |  |  | retention problems - 1) Mkt - google ads (KW, ad, demo, cpa -> position, cpc), device type, 2) price, cancels, 3) Billing - CPD, billing error mix, 3DS, 4) code 5) Merchant Processor | retention problems - 1) Mkt - google ads (KW, ad, demo, cpa -> position, cpc), device type, 2) price, cancels, 3) Billing - CPD, billing error mix, 3DS, 4) code 5) Merchant Processor
[21 empty] | Change settlement email to mc2data@gmail.com | Data Dictionary | Data Dictionary |  |  |  | Refund App | Refund App | Refund App | Refund App | Refund App | Refund App code | Refund App setup | Refund App setup | Refund App setup |  |  |  |  | Are CSRs all paid? |  |  | Are CSRs all paid? |  | Refund App setup
[21 empty] | Customer believes $27 + $1 charge | [5 empty] | 2D vs. 7D results? | 2D vs. 7D results? | 2D vs. 7D results? | 2D vs. 7D results? |  |  |  | 2D vs. 7D results? -> need to restart since CM and LC should be looked @ diff | Coordinate CSR only 1 for 25 hr/week | manual upload of S0 |  |  |  | 3DS Dropped. https://prnt.sc/l4y026 not error codes https://prnt.sc/l4xvha b/c smaller banks https://prnt.sc/l4y5wu fyi wfc has terrible prot % https://prnt.sc/l4yr86
[21 empty] | First CB | [5 empty] | more accurate GA tracking - what kind of analysis can we do now? | Pricing test once 3DS launches (LTV margin is low) | Pricing test once 3DS launches (LTV margin is low) | Pricing test once 3DS launches (LTV margin is low) |  |  |  |  | Pricing test $39.90 once 3DS launches and features (LTV margin is low) AND no welcome message on login |  |  |  |  | retention analysis vs USGA and error code analysis vs USGA for S1.0
[21 empty] | retention metrics | retention metrics | retention metrics - especially remarketing | weekly retention report |  | weekly retention report |  | Confirmed traffic looks normal after d/b changes. Good CR rate day masks if there are any issues but waterfall/javascript errors looks ok | [6 empty] | Billing - daily settlements are not increasing as expected. LiC/LaC look into billing. | Billing - daily settlements are not increasing as expected. LiC/LaC look into billing.
[21 empty] | bounce rate analysis | bounce rate analysis | bounce rate analysis - by UXC | [11 empty] | does bank care about trial and price change? | Ensure MDF4 bug not causing problems in billing, retention forecasts
[22 empty] | Chase merchant statement | Chase merchant statement |  | setup chase MID | setup chase MID - call Joncarlo | setup chase MID - call Joncarlo | Setting up Chase MID | Setting up Chase MID | Setting up Chase MID | Setting up Chase MID |  | Setting up Chase MID | Setting up Chase MID almost done once LaC checks settled descriptor. Ramp transactions on there
[22 empty] | Security Metrics new PCI requirements (TLS 1.1) |  |  |  | Do refunds require auth's now? (see Chase email) | Do refunds require auth's now? (see Chase email) |  |  |  | retention Inmates & Sex offender- compare and separate categories | retention criminal background
Prod | [19 empty] | split test new RR, new SUP (by thurs EOD) | Split test - RR 2.1, SUP 2.1 | Loader performance starting 5/27 | LP perf - new Terry design, pull copy to the top | New CasD for 7D trial. Modify the single PR customer on it and update all the $1 trials and reporting | LP perf - new Terry design, pull copy to the top | LP perf - new Terry design, pull copy to the top | LP perf - new Terry design, pull copy to the top | LP perf - new Terry design | LP perf - new Terry design | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? |  |  | DTR with Quadzero doesn't work because sticky occurs on a declined trans or successful trans. A rule can never be used after the first decline. Code needs override to not use QZ if it is on certain processors. Ultimately we need our own sticky/DTR phase 3.. Fix later |  | Look at gitlab for bug tracking | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ? | Reach out to Experian |  | Conf + Upsell Experian - ID Theft protection, Sex Offender, Unclaimed Funds, Foreclosure info (future, MyAccount) ?
|  | Setup tools |  |  |  |  | GA tracking | TV image/font | TV image | Decide on TV Image. walking in city, mugshots in last iteration | Contact us content | PR GA/GTM | PR GA/GTM | PR GA/GTM, decide on PR conversion points | PR conversion points for RR and Signup, Adwords/Bing Signup Pixels | Adwords/Bing Signup Pixels - same google account as TV - is that an issue? | verifi rules setup and DTR | quick fixes based on reporting |  | train LaC for populating GA data | How to tell original CasD and Remarketing sales | Short $27 (clever) performance starting 5/26 | SUP perf - why empty? remove "Success" copy? | Asian girl 6/9 - did it help bounce rates? |  |  |  | VAE requirements email | clean up SUP once variables available, create new variations for SUP for Sex Offender, Inmate |  | Email+BA+SMS | Email+BA+SMS | Email+BA+SMS | Email+BA+SMS - getting ideas from checkpeople now (fyi their RR looks better now--animated circles for EVERYTHING) https://www.checkpeople.com/public-records?aid=1&tid=65&sid=criminal+records+for+free&gclid=Cj0KCQjwk_TbBRDsARIsAALJSOZZbG-axuS8h6k1_OuKMzhEsWPynLYQM90vIboW3AGgauyDvZk5o94aAs-6EALw_wcB | [5 empty] | Email+BA+SMS CP doesn't remarket... | [5 empty] | Email+BA+SMS CP doesn't remarket...
|  | Go over flows |  |  |  | Revised PR by next week | Review PR | Review PR (Open Sans, SO LP image, leave MHP) | TV GA Setup+Analysis | Clone TF content for PR -> merchant processor | Finish terms/privacy content for PR |  |  |  | target 2 weeks to launch (flows->bugfixes->UXC) | target 1 weeks to launch (flows->bugfixes->UXC) | QA and launch week | get handle on phase 2 optimizations | seo file from enformion | seo file from enformion | Create SUP 2.5 (Long Form) | Long $4.95 performance starting 5/29 |  | Disable test #2/3/4 and switch over to $1-7D vs $1-2D |  | tracking status - TV, People discrepancy |  | Default to become SUP Long+$1 for Report+high disclosure | Some new UXC for Public Records, Background | New UXC for Compet, Inmate (adgroups), Sex Offender (adgroups), Locate (adgroups) | Crim BG UXC - LP, SUP pulls from Background | Crim BG UXC - LP, SUP pulls from Background |  | VMPI as CB% is still a concern. only 1 CB came in from 3DS cust but it was not protected b/c it was not fraud CB. 80+% of CB are fraud CB which is what 3DS protects | [5 empty] | VMPI
| Almost finalized. Clean file to send from mc2data | Show how UXC is accessed |  |  |  | Find new chat for desktop | Setup Thunderbird (Email/Chat/Calendar) | Setup PR UXC | Setup PR UXC | Setup PR UXCC structure | Setup PR UXCC structure | Setup PR UXCC structure | [5 empty] | track reporting for launch and look for bugs | enformion 2nd token | enformion 2nd token |  | Med $4.95 performance starting 5/26 |  | Reporting for 1/2/3/4. #1 to NOT have CasD |  |  | SUP - 1 step? | SUP - 1 step? | SUP - 1 step? | New TV UXC for Compet - how to track conversions on PR | Background UXC - make a parent | Background UXC - make a parent |  | Social? https://www.fullcontact.com/pricing-plans/ ($0.01/match enrich api) https://pipl.com/api/pricing (this one is really very interesting $0.20/match, social+PHOTOS!+lastseen+creationdate+urls, gender, addr, phone, jobs, edu, languages, family) | Fullcontact Social | Fullcontact Social signup for acct and try for free to sample |  | 29v39 test | No 3DS test, processor test
[8 empty] | PR Sales Site | send event if people scroll down 25% on the page |  | VOIP setup phone.com or twilio | VOIP setup phone.com or twilio (used freshcaller instead) | Setup billing for freshcaller after their free trial |  | GA waterfall goals |  | verifi issues with sending transactions | New images for PR LP | process to get back to previous version = notes + daily backups | create up to 20 RM email, same delay |  | create Original Clever | Performance vs. SF (Spyfly) | Performance vs. SF (Spyfly) | Performance vs. SV (SeekVerify) |  |  | some new CM/LC UXC |  |  | Public UXC - make a parent | Public UXC - make a parent |  |  | retention for every ad group (or UXC) from start of time to 17 days ago Pull these groups from PR S0 Waterfall | Mysql for reporting |  | Paul SUP configure and test | Paul SUP configure and test | Interactive on other UXC |  | More Paul SUP tests?
[9 empty] | go through mobile experience through affiliate links (see if TF vs BV vs SV is better) | TV split between TF/SV -> changed to TF/BV |  | Test PF after price change 100%, bounce redirector |  |  |  | decliner passthru/CasD, CasX Remarketing | Remarketing ( + noloader, 2 emails) | Extended Remarketing | should we adopt aggressive pricing strategy? $4.95 f0r today's report and $27.78/mo for unlimited reports (like free credit score) | 1 UXC criminal background (re-use criminal search) |  | Performance vs. TF (via Envyus) - contact Envyus | Performance vs. TF (via Envyus) - we both fail at SUP |  |  |  | CA disclosure |  |  |  | Compet UXC - make a parent | Compet UXC - make a parent |  |  |  | Site uptime. now 2 providers (Cula.io and UptimeRobot) and multiple location pings, multiple providers don't support javascript render with angular |  | Reverse Phone design from Paul. Need data attribute from IT | Reverse Phone design from Paul. Need data attribute from IT | Reverse Phone design from Paul. Need data attribute from IT
[9 empty] | let Verifi know we won't be using vault |  |  | content sales site, member site | content sales site, member site | content sales site, member site | content sales RR/Signup/Opt Out/Unsub/Emails, member only Loader, disable RR | email content Welcome, db Horoscopes retry/discount settings | email tracking through GTM->GA | enformion dev token for staging | RR page |  |  | Feedback on Terry design | TV going to Long $27, not $4.95 | Experian - ID Theft protection, Sex Offender (future) |  | Experian - ID Theft protection, Sex Offender (future, MyAccount) |  | Experian - ID Theft protection, Sex Offender (future, MyAccount) |  |  | PCI Attestation |  | stop particle test+update doc retention crim background | [6 empty] | Experian costs
[12 empty] | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | algorithm for premium upsells (phase 2) | Loader page |  |  | Need UXC for all configs - see Sales Site UXC Info google doc | [8 empty] | Test 3DS no welcome message on login
[12 empty] | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | algorithm for remarketing campaigns and content | need front end developer / designer |  |  |  | add screenshots to DAR |  |  |  | Multibranding? |  |  |  | Test 3DS low grace period if 3DS CR suffers |  |  |  | Test 3DS low grace period if 3DS CR suffers
[22 empty] | Plan to prevent prod error | Plan to prevent prod error | Plan to prevent prod error | [6 empty] | new SUP (Paul design)
Dev | Reviews site almost done. Need front end updated, Privacy, Urls from EnvyUS, UXC needed | C1, URLs, Pixels | URLs, Pixels, B1 flow should not keep re-showing LB | URLs, Pixels | URLs, Pixels | GTM on site, iframable pixel | Bing UET native in GTM | Integrating html | Integrating html | Integrating html | Integrating html | Integrating html | Integrating html | Integrating html | bugfixes | bugfixes | bugfixes for launch | OI |  | Metrics | Email remarketing v1.5 (engagers, gmail different, use results from last teaser, tracking, list-unsubscribe header, manual unsubscribe) | algorithm for Loader timing | Rename tracking variables |  |  | Enformion errors? |  | Terry SUP | Terry SUP -> Paul | Terry SUP -> Paul | cancel vs declines in GA waterfall |  | Google cloud -> Google One | Enformon error | Enformon error |  |  | Upload S1.n | Upload S1.n | Upload S1.n | Hiring dev |  |  | Upload S1.n
| Jody sent back A1*, B1*, C1*. review today | Setup GA and QA | Setup GA and QA | email routing goes to black hole | CPA meeting |  |  |  | IT to give LiC list of items in code not working and I can give Jody feedback about quality of work | gave feedback to Jody and he also gave final work product | background img uxc driven | switch to mosaic pic |  | Content sales site, member site |  | OI | SSL |  |  | SEO |  |  | what is displayed in the daily S0 emails? Name? Description? |  |  | 3DS | 3DS | 3DS | Uploading S1 into Adwords | 3DS | 3DS |  | uptime? | Gateway error | Gateway error |  |  | Retention report |  | Billing ideas | Investigate 3DS drop
| Setup the mc2 cloud. Needs personal configs | All browser QA (Mark to do iphone/ipad) | All browser QA (Mark to do iphone/ipad) | Unreachable/Landing page not found on Adwords when google checks landing pages | status for launch | [5 empty] | back button redirect to third party url + tracking | undo back button redirect after we hear from Google (UXComp) |  | Contact us email |  | PCI scan compliance |  |  |  | Enformion IP |  |  | cache flush schedule @ 1:55AM, campaign will be down from 1AM to 2AM PST |  |  | IT to look at Terry's code quality |  |  | 3DS | Uploading S1 into Adwords (also onetime S0 load before 7/21) | Not recommended by google |  |  |  | Mysql for reporting |  |  |  | SSL expiration+google manuall upload. Please fix root cause for expiration | Hiring dev | Billing ideas
| Vultr fast servers reserved (prod). TV + cloud. $40 + $80/mo google cloud will be for gateway | All reviews numbers to be in the hundreds | <-- done | increase font-sizes of headlines | Chat/Email/Docs/ IT | [5 empty] | Contact us + footer + cards on reg | Contact us + footer + cards on reg |  | MX record check |  |  | test on iphone 5, 8 and 10 | [5 empty] | Enformion error |  |  |  | blling code change |  |  |  | Billing bug - impact? |  |  |  | stats like retention by demo url param | stats like retention by demo url param |  | d/b update risky? coord testing | d/b update risky? coord testing (this is technically done but we should wait until we test rollback to see if code issue) | Investigate 3DS drop | reverse phone |  |  | d/b update risky? coord testing (this is technically done but we should wait until we test rollback to see if code issue)
| small changes to css | wider image for banner so that face is not obscured by text | wider image for banner so that face is not obscured by text, jody emailed alt image | <-- done | status for backend for PR launch | [8 empty] | Loader does not shows names on questions |  |  | test on ipad |  |  | Verifi CB setup | Verifi CB setup |  | CULA report - could our uptime or perf be hurting CVR? | CULA report - could our uptime or perf be hurting CVR? | [6 empty] | Terry SUP -> Paul | Terry SUP -> Paul | Terry SUP -> Paul | Terry SUP -> Paul | Terry SUP -> Paul |  | Paul SUP | Paul SUP fixes (hide step 1 button/seals after success) | PCI Scan | PCI Scan | social addon backend
| Free equiv pingdom setup | Free equiv pingdom setup | Free equiv pingdom setup -> http://cabotapp.com/ + Twilio | make reviews SEO friendly (schema.org, extension links, titles) AND submit to google webmaster tools for SEO | copy changes for landing page changes | copy changes for landing page changes | [7 empty] | report limiter | [5 empty] | Performance | [10 empty] | Terry LP with asian girl b/g | [6 empty] | Hire the Dev | Gitlab
|  | C1. disable (grey) button if required field not completed | C1. disable (grey) button if required field not completed | <-- done | bank transactions/financial | [8 empty] | csr cancel/uncancel | [6 empty] | test token (enformion 2nd token) | sendgrid has access to mc2data@gmail.com (google warning) |  |  |  | not have autofocus on search box on mobile only (for keyboard) | not have autofocus on search box on mobile only (for keyboard) | not have autofocus on search box on mobile only (for keyboard) |  |  | questions about uploading S1 data into Adwords (onetime and recurring load) | questions about uploading S1 data into Adwords (onetime and recurring load) |  |  |  |  | reverse phone | reverse phone | reverse phone | reverse phone
|  | Advertiser disclosure on top of footer | <-- done | review desc block to all link to review page, not just the read review link | small dev project for work | [14 empty] | create team@mc2data.com email alias for us to use. | Terry - doing LP + Loader | Terry - doing LP + Loader | Terry - doing LP. Dev process? | Terry - doing LP. Dev process? |  | Terry - doing LP. Dev process? | [5 empty] | Server capcity - Inmates campaign (total 300 S0, 15K clicks/day) |  |  |  |  | social addon backend | social addon backend | social addon backend | social addon backend
Corp | [5 empty] | Corp Setup | Corp Setup - agent vs member/manager | Corp Setup - FL foreign filing - hopefully Tues/Wed | Corp Setup - FL foreign filing - hopefully Tues/Wed | FL filing complete |  |  | Get paid from EnvyUs | Get paid from EnvyUs | reconcile Envyus |  | Stacy meeting Friday, location? | waiting on stacy thoughts about box product | reconcile sale performance stats - waterfall(GA) vs waterfall(internal) vs. adwords waterfall vs UXC-based waterfall | reconcile sale performance stats - waterfall(GA) vs waterfall(internal) vs. adwords waterfall vs UXC-based waterfall |  |  | Set up wire payment; Pay Terry; Informium. Complete the model |  |  | confirm wire went through | more capital | more capital | more capital | domain xfer from godaddy to google | domain xfer from godaddy to google | domain xfer from godaddy to google | domain xfer from godaddy to google | domain xfer from godaddy to google | domain xfer from godaddy to google |  |  |  | Citi Card having issues? | Higher Limit? (been waiting to reach back out to QP till Thurs) | QP limit is now set to $100.8K/month
| California nexus taxes on kidco / jco |  |  |  |  | people finders contract | people finders contract | credit card account; check for Jasmine personal credit card | credit card account | credit card account - applied | credit card - old account | credit card - old account | [6 empty] | money flow - S0 -> verifi -> bank account |  |  |  |  | MAJOR INITIATIVES : |  |  | check merch proc costs - qualpay admin i/f | check merch proc costs - qualpay admin i/f | check merch proc costs - qualpay admin i/f | credit card with good benefits | domain for inmate search |  | xfer mc2data, privaterecords, truthviewer to google? (after IT gets back) | xfer mc2data, privaterecords, truthviewer to google? (after IT gets back) | xfer mc2data, privaterecords, truthviewer to google? (after IT gets back) | xfer mc2data, privaterecords, truthviewer to google? (after IT gets back) | xfer mc2data, privaterecords, truthviewer to google? (after IT gets back) |  |  | Aggressively pursue reason Chase declined PR $39 transaction |  |  | xfer mc2data, privaterecords, truthviewer to google? (auto renew 11/4)
[7 empty] | mailing address working | PR merch account - BofA and Qualpay after sales site | PR merch account - BofA and Qualpay after sales site | PR merch account - Qualpay and Chase, after sales site and bank account. Qualpay match prices | PR merch account - finish QP. start chase? | PR merch account - finish QP. start chase? |  |  |  | PCI scan | corp paperworks | corp paperworks | IT costs - vpsdime, google cloud and vultr |  |  |  |  | People - not any different than Crim (worse in fact) | [6 empty] | mc2data.com gsuite account (original) | sale emails go to mc2data@gmail.com | sale emails go to mc2data@gmail.com | sale emails go to mc2data@gmail.com | sale emails go to mc2data@gmail.com | daily upload of Verifi transactions
[7 empty] | operating agreement | operating agreement - MC2 and Caesar |  | Washington state - B&O taxes |  |  | Chase merchant account??? | setup chase MID with Verifi | setup chase MID with Verifi | setup chase MID with Verifi | setup chase MID with Verifi | setup chase MID with Verifi | financial model |  |  |  |  | Names - not working yet (still early) | [6 empty] | marketing@mc2data.com email account |  |  |  | check daily settlements - they do not appear to be increasing as expected (proportional to sales) | check daily settlements - they do not appear to be increasing as expected (proportional to sales) | check daily settlements - they do not appear to be increasing as expected (proportional to sales)
| Capitalize $28K for this year, $60K next year, then trust invest 1M | [5 empty] | verifi contract assign | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | spokeo contract | enformion payment | enformion payment hold until we get SEO file/token |  |  |  | Long Form - seems to be better (try RR again? clone CheckPeople via Terry) | [10 empty] | PR Model: No Legacy revenue | QA billing engine |  |  |  | monitor SSL Cert renewal email weekly (ask IT about this)
[7 empty] | Trusts + General Estate Planning Tips/Organization | verifi contract assign | verifi contract assign | verifi contract assign - waiting for bank account | verifi contract assign + setup | verifi contract assign + setup | verifi contract assign + setup | verifi contract setup | verifi contract setup |  |  |  | chase MID |  |  |  |  | Free Trial - $1 working? $4.95 kinda (will need 3DS) | [6 empty] | security re: laptops |  |  |  | research hire vs contractor | research hire vs contractor |  |  |  | Representment success rate? QP says over past 90 days: 14 issuer accepted, 8 issuer rejected, 2 challenged, 41 issuer review Do you see the approx 14 returned in our statements?
[6 empty] | bank transactions/financial | bank/credit card/financial | bank account - go into Chase Tues; gift to trust, which will xfer to bank account | bank account - go into Chase Tues; gift to trust, which will xfer to bank account | bank account - set up at Chase, gift to trust, which will xfer to bank account | [9 empty] | conversations failure, add me back |  |  |  | Envyus - haven't tried yet | [6 empty] | pay USGA for CSR | pay USGA for CSR |  | CSR payment question (Morelia is asking) | pay USGA for CSR
[13 empty] | verifi's merchant info questionnaire | [12 empty] | Delaware company registration - consolidation? |  |  |  |  | Mastercard for testing | BBB | BBB | BBB | BBB |  | BBB | BBB | BBB |  | BBB Update Reg page with Term disclosure
[13 empty] | enformion contract | enformion contract | enformion contract | enformion contract | enformion contract |  |  | Terry | [10 empty] | credit card with good benefits (Aug 12) | credit card with good benefits (Aug 12) | credit card with good benefits (Aug 12) | credit card with good benefits (Aug 12) |  | $100K capital in |  | Check with Chase why no interchange? | Check with Chase why no interchange? | vultr pricing ok?
[31 empty] | Enformion invoice | Enformion invoice |  |  |  | Check merchant processing fees | Check merchant processing fees | Check merchant processing fees |  | Check merchant processing fees
[31 empty] | CheckPeople update | CheckPeople update |  |  |  | Google Data Studio - BI Platform? | Google Data Studio - BI Platform? |  |  | Look for accounting system |  | Look for accounting system | Google Data Studio - BI Platform?
Misc | [8 empty] | Fix chat clients for phones |  |  | does restore actually work (financial model) |  |  |  |  | record CSR voicemail message (Vania?) | when reconciling march enformion, remember we launched 4/17/2018 @3PM PST | set up proxy |  |  | using mc2data @ gmail for shared files, calendars |  |  | snail mail - check weekly | [9 empty] | clean up gmail account |  |  | Switch chat systems? Used only by IT and LC
| PO box with registered agent | [7 empty] | Close old chats (24hp....) room | [12 empty] | mc2data @ gmail shared drive
| Handwrite a note | [8 empty] | send test snail mail to Lionel house to see if PO Box is really slow. 3 days! | test snail mail results?
| check with USGA CSR and phone system | [11 empty] | snail mail | snail mail | snail mail

## Copy of Q1 2019 (hidden)
0 |  |  |  |  | Responsible | Description | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01
Sales Site
| 1.1 design with Paul |  |  |  | MC | SUP | start
| Content changes |  |  |  | LiC/MC | clean up, test $1 trial vs. $1 report | [6 empty] | start
| Test Flows (Loader, RR, SUP 1 step) |  |  |  | LiC | [7 empty] | start
| 2.0 design with Paul |  |  |  | MC | all pages |  |  | start
| Multi-branding |  |  |  | LiC/MC | [5 empty] | start
|  | PrivateRecords |  |  |  | Criminal / Arrest / Jail Records, Background Checks
|  | PeopleSearcher |  |  |  | People Locate, Reverse Phone SEO
|  | SearchPublic |  |  |  | Public Records, Court / Police Records
|  | TruthViewer |  |  |  | Cheating, Online Dating, Reviews site (background checks, SEO)
| Conf Modal |  |  |  | LiC | conf+SSI (pdf download, target monitor/updates, target upgrade) |  |  |  | start
| Upsells |  |  |  | LiC | need ID protect, credit monitoring, Advertising, target upgrade |  |  |  | start
| Price Testing ($39, Quarterly, etc) |  |  |  | LiC | Need 3DS, Retry Optimization |  |  | done
| Remarketing Sources |  |  |  | LiC/LaC | Email optimization, BA, SMS |  |  |  | start
Billing and CB's
S1 Upload
| 3DS |  |  |  | LiC/IT |  | done |  |  | start
| VMPI |  |  |  | LiC/IT |  |  |  |  | start
| Retry Optimization |  |  |  | LiC/IT | Items like retry in morning, best days to retry, etc |  |  |  |  | start
| MIDs / Signatures |  |  |  | LiC | needed after Multi-branding | [6 empty] | start
| Downselling |  |  |  | LiC | CSR % discount or straight dollar | [6 empty] | start
SCORE |  |  | VALUE | EFFORT
Member Site
5 | Reverse Phone Lookup |  | 3 | 2 | LiC | n/a |  |  | start
6 | Real Time Monitoring+PDF |  | 3 | 3 | LiC | Enformion? |  |  | start
3 | Sex Offender |  | 2 | 1 | LiC | Experian |  |  |  |  | start
3 | Unclaimed Funds |  | 2 | 1 | LiC | scrape |  |  |  |  | start
3 | ID Protect |  | 1 | 2 | LiC | Experian |  |  |  |  | start
4 | ID Insurance |  | 1 | 3 | LiC | Experian |  |  |  |  | start
2 | Property Data |  | 1 | 1 | LiC | Atom / Corelogic / Enformion |  |  |  |  | start
5 | Social |  | 3 | 2 | LiC | scrape / Experian |  |  | start
2 | Free Membership |  | 1 | 1 | LiC | need Advertising | [6 empty] | start
3 | Credit Score |  | 2 | 1 | LiC | Experian | [6 empty] | start
1 | Mobile App |  | 1 | 0 | LiC | n/a | [6 empty] | start
Report on Cheaters
https://www.searchenginejournal.com/google-introduces-new-search-engine-for-finding-datasets/268337/
Advertising
| Adsense |  |  |  | LaC | [6 empty] | start
| RTO |  |  |  | MC/LaC | [6 empty] | start
| Foreclosure |  |  |  | MC/LaC | [6 empty] | start
| Credit Score |  |  |  | MC/LaC | [6 empty] | start
| Credit Repair |  |  |  | MC/LaC | [6 empty] | start
Credit Card
Home Security
IT
| Performance |  |  |  | IT | After POC, before scaling, determine storage colo vs cloud -- NV? 15K clicks OK | [6 empty] | start
| Uptime |  |  |  | IT |  |  |  | start
Reporting
| Retention |  |  |  | LaC | This is both driving enough traffic to analyze and analyzing |  |  | start
| BI Tool |  |  |  | LaC | [5 empty] | start
Customer Service
| CSR App |  |  |  | LiC/IT | [7 empty] | start
| Hire CSR #1 |  |  |  | LiC |  |  |  |  | start
| Hire CSR #2 |  |  |  | LiC | [6 empty] | start

## Q1 2019 (hidden)
|  |  | Responsible | Description | Gitlab Issue | Value | Effort | Effort (calc) | Total Points | Status | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01
Marketing
New channels
|  | Bing |  | small %, according to Peoplefinders |  | 4 | 3 | 3 | 7 | failed | 2019-11-01: failed
|  | Envyus |  |  |  | 5 | 2 | 4 | 9 | done | 2020-02-01: done
|  | Incent channels | [7 empty] | not started
|  | Display |  |  |  | 3 | 3 | 3 | 6 | failed | 2019-09-01: failed
|  | Remarketing Sources | LiC/LaC | Email optimization, BA, SMS |  | 2 | 4 | 2 | 4 | wip | 2020-03-01: started
|  | Facebook |  | Peoplefinders has not done this |  | 3 | 4 | 2 | 5 | not started
| Reactivate paused campaigns |  |  | Arrests, Jail, Court, Crim, etc using ROAS in account #3 |  | 2 | 2 | 4 | 6 |  | 2019-01-01: done
| Campaign optimization |  |  | Pub Rec |  | 3 | 3 | 3 | 6 | done | 2019-01-01: wip
| New campaigns |  |  | Compet. Peoplefinders suggested online dating, (cheaper CPCs than "Background") |  | 3 | 2 | 4 | 7 | not started
| Demographic targeting |  |  | Create demo-specific campaigns (assuming different demos have different LTV) |  | 3 | 5 | 1 | 4 | done | 2019-11-01: done
Bid strategy
|  | ROAS |  | targets high retention users. Try on CrimBG, PplSrch |  | 3 | 1 | 5 | 8 | not started | 2019-01-01: done
|  | Target CPA vs. Max CPC? |  | we will spend max amount (vs. guessing now). Try on Inmate, BG |  | 1 | 1 | 5 | 6 | done | 2019-01-01: n/a; 2019-12-01: done
|  | try Manual CPC (for retention)? |  | eliminates targeting of low retention users (theory). Try on paused campaigns |  | 3 | 1 | 5 | 8 |  | 2019-01-01: done
Sales Site
| SUP |  | MC
|  | Interactive SUP |  | works for BG, but not for Sex; try on CrimBG, Ppl, Court, PubRec; try 1-step |  | 2 | 2 | 4 | 6 | done | 2019-01-01: wip
|  | Checkout Page |  | SUP that simply takes the order (PII, cc form) without any selling (the assumption is that the users are ready to buy since they got through a very long sales funnel) |  | 1 | 2 | 4 | 5 | not started
|  | Prepaid cards | LiC | refuse prepaid cards, ask for alternative card | https://gitlab.mc2data.com/root/Dev/issues/67 | 4 | 3 | 3 | 7 | wip | 2019-01-01: wip
| Price / Offer Testing |  | LiC
|  | Trial |  | $9.95 trial, 50% off $29 monthly price |  | 3 | 3 | 3 | 6 | not started
|  | Trial |  | 5-day trial | [5 empty] | not started
|  | Monthly |  | $29 vs $39 vs $19. Currently waiting for $29 vs. $39 split test data to age, but we do have all of Pub Rec @ $29 |  | 2 | 2 | 4 | 6 | done
|  | Immediate Billing |  | with LTV's so low, would it be better to do 1-time report fees, with heavy email marketing to get people to buy additional reports. This is the "right way" to sell reports | [5 empty] | failed
|  | PeopleFinders |  | cancellation fee of $3.95 if cancel in trial, 3 price-points: monthly, 3 month (paid upfront) and single report. With single, have an upsell (in their account, pop up offer or email offer) into a monthly (ours is 50% off 1st month). Need to wait on UPSELLS | https://gitlab.mc2data.com/root/Dev/issues/115 | 4 | 4 | 2 | 6 | not started | 2019-01-01: waiting
|  | Spokeo |  | copy Spokeo and others = $1 report + free trial membership ($29/mo) |  | 3 | 2 | 4 | 7 |  | 2019-01-01: done
| Test Flows |  | LiC | copy competitors (must have tested)
|  | Loader |  |  |  | 2 | 4 | 2 | 4 | done
|  | RR |  |  |  | 2 | 4 | 2 | 4 | done
| Multi-branding |  | LiC/MC | initially goes to 1 member site?
|  | PrivateRecords.net |  | Criminal / Arrest / Jail Records, Background Checks |  | 3 | 4 | 2 | 5 | done
|  | PeopleSearcher.com |  | People Locate, Reverse Phone, SEO |  | 3 | 4 | 2 | 5 | wip
|  | PeopleSearch123.com |  | Public Records, Court / Police Records |  | 3 | 4 | 2 | 5 | wip
|  | BackgroundCheckers.net |  | Criminal / Arrest / Jail Records, Background Checks
|  | TruthViewer.com |  | Cheating, Online Dating, Reviews site (background checks, SEO) |  | 3 | 4 | 2 | 5 | wip
Retention and CB's
Retention / LTV
|  | Cancel UX for retention | LiC | don't prevent C0's yet | https://gitlab.mc2data.com/root/Dev/issues/110 | 4 | 3 | 3 | 7 |  | 2019-01-01: done
|  | Retry Optimization | LiC/IT | retry and billing policy by CPD |  | 2 | 2 | 4 | 6 | not started
|  | Upsells / Conf Modal | LiC | conf+SSI (pdf download, target monitor/updates, target upgrade); show only a subset of comprehensive report so we can upsell the rest; need ID protect, credit monitoring, Advertising, target upgrade |  | 5 | 4 | 2 | 7 | wip
|  | Downselling | LiC | CSR % discount or straight dollar |  | 3 | 3 | 3 | 6 | not started
|  | S1 Upload |  |  | https://gitlab.mc2data.com/root/Dev/issues/116 | 3 | 3 | 3 | 6 |  | 2019-01-01: done
|  | Account Updater | LiC | Account Updater |  | 3 | 2 | 4 | 7 | not started
| Chargebacks | [6 empty] | 6 | 6
|  | 3DS | LiC/IT |  |  | 3 | 2 | 4 | 7 |  | 2019-01-01: done
|  | VMPI | LiC/IT |  |  | 4 | 4 | 2 | 6 | failed | 2019-01-01: wip
|  | MIDs backup | MC | need backup MIDs for cancel UX. Use Craig (Esquire + TRX) |  | 4 | 2 | 4 | 8 | ? | 2019-01-01: wip
|  | MIDs / Signatures | LiC/IT | need more after Multi-branding, with different signatures |  | 4 | 2 | 4 | 8 | started
Member Site Features
| Enhance Report Page |  | LiC | information sort order + sticky - used for Enformion negotiations | https://gitlab.mc2data.com/root/Dev/issues/113 | 3 | 2 | 4 | 7 |  | 2019-01-01: done
| More Information on Report Page |  | LiC | OJ Simpson Project | https://gitlab.mc2data.com/root/Dev/issues/118 | 4 | 2 | 4 | 8 | done | 2019-01-01: wip
| Social Data |  | LiC | Full Contact data | https://gitlab.mc2data.com/root/Dev/issues/1 | 4 | 3 | 3 | 7 | done | 2019-01-01: ready
| Reverse Phone Lookup |  | LiC | ready | https://gitlab.mc2data.com/root/Dev/issues/48 | 4 | 3 | 3 | 7 |  | 2019-01-01: done
| Live Monitoring+PDF |  | LiC | ready | https://gitlab.mc2data.com/root/Dev/issues/83 | 3 | 3 | 3 | 6 | done | 2019-01-01: wip
| Inmate Data Source |  | LiC | Scrape data ourselves, vinelink.com | https://gitlab.mc2data.com/root/Biz/issues/58 | 3 | 4 | 2 | 5 | wip | 2019-01-01: wip
| Unclaimed Funds |  | LiC | Scrape data ourselves, https://www.unclaimed.org/ | https://gitlab.mc2data.com/root/Biz/issues/59 | 3 | 4 | 2 | 5 | not started
| ID Protect + Insurance |  | LiC | Experian or TU - use iframe solution; useful for the people searching themselves (which might be significant) | https://gitlab.mc2data.com/root/Biz/issues/61 | 3 | 2 | 4 | 7 | done
| PDF downloads (upsell dependent) |  | LiC |  |  | 2 | 1 | 5 | 7 | done | 2019-01-01: waiting
| Credit Score |  | LiC | Experian or TU - use iframe solution |  | 2 | 2 | 4 | 6 | not started
| Sex Offender |  | LiC | Scrape data ourselves |  | 2 | 4 | 2 | 4 | wip
| Property Data |  | LiC | Atom / Corelogic / Enformion |  | 1 | 4 | 2 | 3 | not started
| Mobile App |  | LiC | n/a | [5 empty] | not started
| Free Membership |  | LiC | need Advertising | [5 empty] | not started
| Report on Cheaters |  | MC | [6 empty] | not started
| Non-data related features |  | MC | https://www.searchenginejournal.com/google-introduces-new-search-engine-for-finding-datasets/268337/ | [5 empty] | not started
Customer Service
| CSR App |  | LiC/IT | Make it easier to use, collect customer data |  | 3 | 4 | 2 | 5 | wip
| Hire CSR |  | LiC |  | https://gitlab.mc2data.com/root/Dev/issues/106 | 4 | 3 | 3 | 7 | done | 2019-01-01: wip
Reporting
| Retention |  | LaC | complete semi-automatic report for CPD, casD, CPA (from DAR) |  | 1 | 2 | 4 | 5 | done
| DAR |  | LaC | automate using google API |  | 1 | 4 | 2 | 3 | done
| BI Tool |  | LaC |  |  | 1 | 4 | 2 | 3 | not started
Advertising
| Adsense |  | LaC | [6 empty] | not started
| RTO |  | MC/LaC | [6 empty] | not started
| Foreclosure |  | MC/LaC | [6 empty] | not started
| Credit Score |  | MC/LaC | [6 empty] | wip
| Credit Repair |  | MC/LaC | [6 empty] | not started
| Credit Card | [8 empty] | not started
| Home Security | [8 empty] | not started
IT
| Performance |  | IT | After POC, before scaling, determine storage colo vs cloud -- NV? 15K clicks OK
| Uptime |  | IT

## Strategy 2019 (hidden)
Strategic Analysis
Our customer acquisition "success" suggests a big TAM, and we have the platform to acquire lots of customers, relatively inexpensively
google said that the big competitors (e.g. Truthfinder, BeenVerified) are spending $100K per day, while the medium ones are spending $50K per day
we were unable to acquire customers at $27 immediate billing
we had to go black-hat at $1 trial, $29/month (now $39/month)
High cancel rates suggest customers are only willing to pay $1 for a single report i.e. they are NOT interested in a subscription product
combined with our customer acquisition success, that suggests weak value proposition -- customers don't get what we (or our competitors) promise.
High CB rates suggest we are charging too much at $39 (and maybe $29)
82CB's @ 2.0% in Oct, 2.4% so far in Nov
my gut tells me this is a $9.95 / month product (or more accurately a $9.95 one-time fee)
High decline rates suggest we sell to the impulsive, uninformed, lazy i.e. subprime consumers
Can we introduce subscription features?
Copy what everybody else has done e.g. Spokeo, Truthfinder, etc
Copy what MyLife has done re: the reputation score of yourself
Add features that are tied to the member's ID e.g. credit score in subscription, upsell credit / ID monitoring.
Create a feature where people can report cheaters. How do you verify? Lawsuits? e.g. cheatersfile.com, ratemymates.com
Can we generate subprime revenue in other ways?
A good example is BetterFuture.com which generates revenue as lead gen to employers (since job-seekers often do background checks, on themselves). See https://www.entrepreneur.com/article/319647.
Background Checkers - jobs
Cheating - report on cheaters? Ad supported?
People Search - private investigators? lawyers?
Inmate Search - bail bondsmen?
Criminal Backgroud - ?
Or just assume subprime consumers like credit repair, credit cards, cheap homes, etc
how many emails do we capture? 10% of visitors = 450 per day = 13.5K per month
Can we manage chargebacks?
CB Ratios are very high (compare vs. USGA)
VMPI, trans adders?
How have we performed?
Considering so few resources P/T, we've done well
We've created a good platform, but still missing many features
We are good operationally, but not great (UXC flexibility, mistakes, reporting, uptime)
We have created a poor UX (product, customer service, aggressive billing)
Strategic Options
Improve the current business
Requires investment (annually)
HIre Prod Mgr = $100K - 150K, Engineer(s) = $100K, 2x CSRs = $50K
Product = $100K for data, hosting
50% chance this will be successful
If successful, transition to full time
do we transition to full time NOW i.e. is it chicken-and-egg where we need to go full time to make the business succeed?
Shut down the current business
Go back to old jobs and integrate in to the old platform
Cut our losses, Investor loses initial investment of $440K minus tail
Make it a side-business
Spend 10 hours / week, Keep your full time job
Make a little extra money
Start New Business (shut down the current business)
See ideas below for New business - only 1 that has been considered is Wellness Pro (need more ideas)
Requires investment
Hiring = CEO, branding, others = $500K
Marketing = $2M
Restarts the clock on freedom.
25% chance new business will be successful.
Do we need to go full time to give this a chance of succeeding?
Worth considering if you don't believe in the current business
New business + Side business (current)
Would require new investment to start new business (see above)
Might get lucky with current, side-business = 10%
Reduces chance of new business succeeding (assume 80/20 split in our work effort)
Requires more effort on our part
Do we need to leave current roles?
| Improve Current Business and Start New business |  |  | People Search + Credit Score + Lead Gen
Would require biggest investment (new + current)
Hiring = $850K
Marketing = $2M
Making a big bet
requires leaving old jobs
worth considering if you trust what has been accomplished so far
Consensus Plan
Conserve cash
pause unprofitable campaigns
lower Target CPA's on unprofitable campaigns
Small Ideas
$3.95 for trial, then $39.95 per month
use Google Maps on SUP
Fake Freemium model
SRP provides teaser = name, age
Step 1 asks user to create account, with no silouhette
completing Step 1 moves to Step 2, which provides the FREE report = DOB, AKA, relatives, all locations, sex offender. Make this big. Then have heavy promotion for hidden sections, asking for credit card
Member Site shows Premium Report
Fixing high bounce rates
could the market just have high bounce rates? Maybe users are expecting to see a government website or actual public records, and not a commercial website. That suggests we need to change the ad copy and bring in more qualified traffic
In that case we need to really focus on Remarketing. CasX campaigns, Retarketing for Google, Remarketing for email, Browser Alerts
Reverse Phone as a feeder to remarketing
New Sales Site - do we have a sales site with no teaser
Default SRP - celebrities in their IP geo
Sign up page - Users are hitting the view report button without entering credit cards. That's because they waited so long that they believe the reports is there's and they have a right to it, and they're just hoping that clicking the green button will get them the report. We do not tell them explicitly that they have to pay to view the report. Copy needed to tell them that.
Do what the credit score companies do, Market the credit score as free with the purchase of a monitoring continuiti monthly membership. So we will sell the first report for $4.95, with the purchase of a unlimited membership that is $27.78 per month. Will have to write the disclosure very carefully, and have to get 3 DS working

## Strategy 2020 (hidden)
Status
Marketing getting low CPA's, with about 200 sales / day
Retention is low at 37%, but has gotten lower recently. Unpredictable
Business is barely break-even, but that does NOT count salaries
Would be unprofitable with full headcount and overhead
Next Steps
Need to know if this is a viable business or not (asap)
We are 2.5 years in to the business
much slower than expected
Success in People Search is ??? (I think 33%)
is that due to us? or the market?
we haven't tried to improve product
we haven't tried new channels
We are short-staffed
Lack of ability / willingness to commit huge start-up hours
We need more people
2020 Plan
Invest funds ($000's)
|  | 600 |  |  |  | Total investment | 1050
keep equity as-is
use funds primarily for staffing, and data deals
no more investment available
HR
FTE for Lionel and Ivan beginning Jan 1
FTE for Lauren beginning July 1
Hire
Web developer - both graphics design and front end coding
USA or Canada
might need to hire 2 people part time (if we have to split up the role)
Product manager
TBH - Mark is not available
Org Chart
Who's the CEO
MC2 to remain CEO temporarily (6 months)
LC to take over (co-manage during 6 months)
Goal
Complete People Search Plan (stuck w/ Enformion until April 2021)
Business is sustainable starting 2021, absorbing full salaries and overhead (office?)
Per-unit contribution margin = $5+
Improve per-unit economics
Marketing
Can't lower CPA anymore but can we increase LTV? Competitors are doing that
Immediate billing
Need to test since this is the future, and competitors are doing that
Billing engine
SSI, 3DS are prime suspects but limited upside
Upsells
Needed for CB mgmt, but will add small revenue (which may be big margin enhancer)
Product
Need to have a better product, should improve cancel rates and CB rates
Product Development
More Data
More Features
Ancillary Features
Unclaimed Funds
|  |  | Credit Score |  |  | soc2 compliance?
ID Protect
etc
Options if goal if not met (after spending $600K)
1. shut down
MC2 loses investment
Team has to find new jobs
2. invest more funds
business looks good, but just needs more funds
any investment would dilute the equity, so MC2 would get more equity
based on company valuation = average of 4x EBITDA and 1x Net Revenue
3. plan B
Other vertical e.g. credit
Credit in Canada?
note this is a possibillity NOW
B2B billing engine
with Credit Canada
Lead Gen
Org Chart and Salaries
|  |  |  | Responsibilities | Salary 2020 ($000's) |  | Equity
MC2 |  |  |  | Strategy, Advisor, Investor | 0 | 30 hours / week | 75% | 65% | 55%
Lionel |  |  |  | CEO | 150
| MC2 |  |  | Marketing | n/a | Lauren will help
| TBH |  |  | Product | 100
|  | TBH |  | Frontend Dev (USA) | 90 | we need this! how much salary?
| Ivan |  |  | Tech | 150 |  | 9% | 12.33% | 15.67%
|  | TBH |  | Backend Dev (offshore) | n/a | do we need this person? not now
| Lionel |  |  | Ops (Config, Billing, CSR, etc) | n/a |  | 9% | 12.33% | 15.67%
|  | Lisa |  |  | 40
|  | 2 | CSR's (offshore) |  | 50
| Lauren |  |  | Finance, BI | 75 | only 6 months | 7% | 10.33% | 13.67%
| Sub Total |  |  |  | 655 |  | 25% | 35% | 45%
|  | Existing Salaries |  |  | 90
| Net Increase |  |  |  | 565
| Other uses of funds (e.g. data, misc) |  |  |  | 35
Total Investment |  |  |  |  | 600
Notes | [10 empty] | LiC | Ivan | LaC
| 1 | Do you want us to go in to Credit? (since it's a good chance we can be profitable in that space) | [8 empty] | No. Too risky in my mind to do direct credit where we are the product. I don't think that lead gen only fits any of our wheel houses currently but it certainly does not have the same equity dilution risk. Lead gen only credit is second to PS. I do understand this singular choice probably has the largest effect on both the future of the business and the co-founder futures. I'd like to learn more about source of traffic for some of these lead gen companies as I doubt it is search. If not search, then risk of failure goes up in my mind even if we hire a marketer with experience in that channel. | OK getting in to Credit now | concerned with Resources
| 2 | Should we continue to work hard on making People Search work? Or should we kill it, or think of it as a side business (since it's not working as is)? | [8 empty] | Yes. I think we have been tiptoeing at least for the past 5 months once we had a CB shock and then the retention shock. Need some more dramatic changes to make step gains. This includes product improvements but also marketing. Right now we have option value to make PS work. If we relegate this to a side business now, we essentially waste that option value as next year it will only get harder with the Visa mandate. Once that occurs we will not want to push this forward and since we have not widened the margins, I can see us not wanting to even keep this as a side business. | Let's make it work | Let's make it work
| 3 | Are you willing to come over FTE, knowing MC2 might go out of business in the future? (and if that happens, you'll need to find another job) | [8 empty] | Yes | Yes | Yes, but in the future
|  |  | If you are willing to come over FTE, how much salary do you need? | [7 empty] | 150K | 150K + health insurance | 150K
|  |  | Are you able to do more than you are doing now? If so, how many hours per week? | [7 empty] | As FTE it will be 60-70 | 70 -80
|  |  |  | PTE | [6 empty] | 25 | 40 | 15
| 4 | What are your thoughts on hiring?
|  |  | Who should we hire now? Front end engineer? Back end engineer? Marketing? Product? | [7 empty] | Both routes will need A) front end engineer B) designer at least
|  |  |  | How much salary do we have to pay for each of these new hires? | [6 empty] | TBD
|  |  | What do you think about our original partner coming back to work on Marketing, Product? (low/zero salary initially) | [7 empty] | I'm open to it in product. I still have my hesitations and I do believe that bringing him on this second time is almost assuredly a one way street. Worst case scenario is that it would be essentially the same as EBITDA dilution instead of equity dilution. It is just a risk assessment that worst case scenario is least likely to occur with him in product. If worst case occurs in product, we don't ship the product. If worst case happens in marketing, it may be hard to reverse.
|  |  | Who should be our CEO? Lionel? New guy? e.g. https://www.linkedin.com/in/vishal-bhalla/ | [7 empty] | I would like to give it a try as CEO. Vishal's track record is impressive. Why did he leave better mortgage? I'm assuming he left lumosity because of the lawsuit from marketing (the marketing claims which caused the suit were probably initiated before his tenure there, but it sounds like he definitely scaled the use of those claims)
Lionel's feedback |  |  |  |  | Ivan's feedback |  |  |  |  | Lauren's feedback
| Does not want to do Credit |  |  |  |  | Willing to do Credit |  |  |  |  | Concerned about going in to Credit
|  | Credit is too risky, particularly for losing equity in MC2 |  |  |  |  | Looking for highest ROI, based on the amount of work we do |  |  |  | Wants to make People Search work
| Wants to make People Search work | [5 empty] | If Credit gets us the highest return, then let's do it |  |  |  |  | Likes Lionel's idea of doing this in phases
|  | Step 1. Increase EBITDA |  |  |  | Wants to make People Search work |  |  |  |  | Willing to come over FTE
|  |  | Do this by increasing sales. Even though our sales are low margin, they are still profitable and so increasing sales will increase EBITDA, which will support FTE |  |  |  | Believes we will make improvements in billing, such as turning OFF 3DS |  |  |  |  | Should not come over same time as Lionel or Ivan
|  | Step 2. FTE for Lionel and Ivan |  |  |  |  | if we do that, we will require more MID's (could work with different brands, different signatures) |  |  |  |  | Believes we need to make scarifices / take risks (to get reward of ownership)
|  |  | need $150K salary |  |  | Willing to come over FTE, with risk |  |  |  |  | Headcount
|  | Step 3. Improve retention |  |  |  |  | need $150K |  |  |  |  | OK with original partner
|  |  | Note sure how...could be immediate billing, different marketing hooks, ROAS, etc |  |  |  | need health insurance
|  |  | What about improving product? How committed are you to that? |  |  | Headcount
| Headcount | [5 empty] | Concerned about original partner's capabilities / distraction but is open minded
|  | Will think about original partner |  |  |  |  | We can always terminate him if he is a distraction
Will allocate more time to MC2. How much?

## Strat mid 2020 (hidden)
2020-05-01
What have we learned?
We can survive, succeed in this space
Can we become a tier 2 player (PeopleFinders, which is 15x our size) or a tier 1 player (BeenVerified, which is 80x our size)?
Strategy
Dominate Subprime People Search space
a space that the big competitors don't seem to address
we know it well, and the momentum we have now is for the subprime
New Who | Who | Function |  | Current | Importance | Score | Comments
LaC' | TC | Marketing (Google) |  | Strength | 10 | 9 | strong sales, low CPA
LC/LaC | TC / LC | Marketing (Envyus) |  | Strength | 10 | 9 | need Pub tracking but strong relationship, especially if we get the contract done
| LC / IT | Billing Engine |  | Strength | 10 | 9 | sophisticated billing, that we control 100%
| LC | Split Tests |  | Strength | 8 | 8 | can test almost anything, just need volume
| TC | Sales Site / CVR Optimization |  | Strength | 8 | 8 | good but need better UX, more flows, simplified UXC mgmt
| LC / TC | Data |  | Weakness | 8 | 5 | currently a weak partnership w/ Enformion (weak data, expensive) | Good oppty for cost savings and better product. We lack knowledge / skills, so will need biz dev
TC | N/A | Marketing (Bing, FB, Criteo, Display, SMS, Remarketing) |  | Weakness | 6 | 2 | we don't have the knowledge / skills | Unclear oppty but will have to hire or use external partners.
TC | N/A | Cross Sell / Upsell |  | Weakness | 6 | 1 | more important for this vertical vs. Industry? currently CPSSI | Unclear oppty but don't know how to solve. Do we have to hire?
LaC' | TC / LC / IT | Staffing / Hiring |  | Weakness | 8 | 1 | we lack capabilities to accomplish our goals, and don't have recruiting skills | Unclear oppty to improve company w/ great talent
| LC / TC | Multibranding - (JC, RC, LC, Art1, Art2, Art3, MC) |  | Opportunity | 10 | 5 | tried but failed. Need to clean up, no bread crumbs | Great oppty to increase capacity - becomes our key value add, and we have knowledge/skills
MC | LC / TC | Merchant Processing - capacity, costs |  | Opportunity | 10 | 6 | currently paying too much, not enough capacity | Great oppty to lower costs, we have experience / skills but need to build up history / relationships. Dependent on Multibranding
LC | N/A | Marketing (External Partners such as Fluent, RXMG, Xanadu, etc) |  | Opportunity | 10 | 5 | haven't tried yet, so a neutral score | Great opportunity to make a big impact. Dependent on Multibranding
MD'/MC/LC | TC | Product UX |  | Opportunity | 8 | 3 | current Membersite bad; the new Membersite UX is looking good | Great opportunity to reduce cancels (killing GSR today). Worried about data compromising UX
MC | LC | CSR |  | Opportunity | 6 | 5 | haven't spent enough time developing the systems | Good oppty with our knowledge / skills. Strategic choice for Philippines is the right choice
| LC | Reporting |  | Opportunity | 6 | 5 | haven't spent enough time -> slow reporting, with holes in our reporting | Good oppty with our knowledge / skills
| TC | Google Double Serving |  | Opportunity | 6 | 1 | tried, but failed | Good opportunity if we can make this work
| TC | ID Protection |  | Opportunity | 4 | 5 | promising conversations with Privacy Maxx | Decent opportunity to add some product value
MC | TC / LC | MID Aggregation |  | Threat | 10 | 8 | currently not many MIDs but will be a problem as we scale | Multi Branding (100% Perfect) solves that
TC | N/A | General Free Trial Model |  | Threat | 8 | 5 | currently we rely on this model (under attack), while competitors don't | No solution until we figure out Immediate billing (failed). Dependent on Multibranding
| TC | FTC Low Disclosure |  | Threat | 6 | 5 | currently low volume, few complaints | Need to test higher disclosure, dependent on Multibranding
| ALL | TC Departure |  | Threat | 8 | 4 | set for Dec 31, 2020 | Need to hire / train - Product, UX, Marketing, Biz Dev, Problem Solving
MC | TC | MC Unmasking = google, envyus |  | Threat | 10 | 6 | currently only suspected by Enformion but Envyus is a risk | Multi Branding (done 100% perfect) solves
| TC | ART Timeline Discovery = Equity Takeover from Industry |  | Threat | 10 | 5 | currently suspected with some data; recent outreach but don't know why | Artemis biz plan or something else?

## Q1 2020 (hidden)
|  |  | Value to us | Weeks of Work | Priority | Milestone | Comment
Product Development
| Internal Gateway |  | 2% | 4 | 6
| Multi Brands |  | 30% | 8 | 5
|  | CSR |  | 1
|  | Email |  | 4
|  | Calling System |  | 3 |  |  | LC = bottleneck
Features
|  | Immediate Billing 1.5 | low? | 2 | 9
|  | Sex Offender | low? | 2 | 3
|  | Inmate | med? | 2 | 4 |  | MC = bottleneck
|  | cheaper Enformion for casD | 1.5% | 1 | 2
|  | cross sell ID Protect or Credit - PDP Lightbox | med? | 0.3 | 1 |  | MC = bottleneck
Second Credit Card
Remarketing
|  | SMS | 2% | 3 | 7 |  | MC = bottleneck
|  | BA | 1% | 3 | 8 |  | MC = bottleneck
| Reporting 2.0 |  | low? | 2 | 10
27.3
Build 5
Envyus reporting
CP SSI fix -> launch
MID closing capability
scrub casP capability
affiliate fraud tracking (phase 1)
Retention by affiliate
Build 6
Member Site March 2020

## Q3 2020 (hidden)
Theme: Scale and operationalize the business while taking baby steps to secure our long term competitiveness
Category | Project | Gitlab | Description | Benefit - with probability | Dependency | Total Points | Impact | Dev Effort | Ops Effort | Effort (calc) | Status | Responsible | Comments | Hide
Corp | Hire developers and marketing |  | We need developers to work on projects | Faster development - H |  | 28 | 20 | 1 | 3 | 8 |  | NP
Product | Lower core data costs |  | Find new vendors and compare vs. Enformion. Renegotiate Enformion. | Product Cost - MH |  | 27 | 18 | 1 | 2 | 9 |  | TC
Corp | WeInform.net for internal use |  | transition our internal ops to WI (email, files, gitlab, bugzilla?) |  | getting credit card for WIL | 26 | 18 | 1 | 3 | 8 |  | PP
Corp | MBMC |  | Create and operationalize the maintenance of new entities and get MIDs |  |  | 26 | 18 | 1 | 3 | 8 |  | TL
Product | Obituaries Hack |  | Add "Want Death Records?" to PDP that pops up a Contact Us form -> emailed to us. We (Demetri?) manually scrape competitor sites and email results to customer. Combine with effort to migrate emails to d/b | Learn if Obits info reduces cancel rates - H | Demetri to process | 26 | 19 | 1 | 4 | 7 |  | MC
Product | Inmate Hack |  | Redirect Inmate customers to a prisonpro.com clone (see traffic https://prnt.sc/t051wc) we create at privaterecords.info, using wordpress. | Learn if Inmate features reduces cancel rate - H | Ryan C / Mark C to create | 25 | 17 | 3 | 1 | 8 |  | MC
Product | UX 1.5 |  | Minimal brand differentiation such as cloning a compet in order to get enough differentiation to create new brands/MIDs. This is NOT focused on fooling Envyus or google as that is UX 2 | Sales and sales diversification |  | 25 | 16 | 2 | 1 | 9 |  | TL
Product | Membersite Mar 2020 |  | New Membersite (comprehensive) | A nicer design will reduce cancel rates - M | Hire Front End Dev | 23 | 18 | 5 | 2 | 5 | 20% | TC | design by Melissa, front end by new Korean dev, back end by IT. Need data providers like Ancestry.com
Product | Obituaries |  | Add Obituaries to Member site with IDI or manual scraping (could test concept) | Obituary data and features will decrease cancels for our highest volume use case (20%) - M | Data deal, see what we learn from Obituary Hack | 23 | 17 | 4 | 2 | 6 |  | TC
Marketing | New Use Cases / Campaigns |  | Need to support new campaigns - NAMES (GAC google support), Reverse Phone (sales site), Online Dating (Native Ads) | These campaigns will generate 10% - 20% more sales at same CPA - M | n/a | 23 | 17 | 2 | 4 | 6 | 0% | TC | Try ad customizers in google - https://support.google.com/google-ads/answer/6093368
Product | Membersite Data Upsells |  | Sell PS report for $0.23, then upsell ala carte items based on Enformion's Indicator "Meta" Data | Customers will purchase upsells ala carte - H | New Membersite | 23 | 16 | 3 | 2 | 7 | 0% | MC
Corp | Lower compliance risk |  | Disclosure testing that minimally impacts conversion rates. Cancel funnel testing that is more compliant but maintains a low cancel rate. |  |  | 23 | 15 | 1 | 3 | 8 |  | TL
Tech | UX 2 |  | create a new UX 2 (BV) that looks different than UX 1 (used for PR). | Envyus will not link UX1 = UX2, Double serving can increase sales - M | n/a | 23 | 14 | 2 | 1 | 9 |  | PP
Billing | Fraud Protection |  | Tools to manage affiliate fraud risk. Build (inidcators like time on site) vs Buy (NS8 or SIFT) | Ability to scale and lower CB risk |  | 22 | 13 | 2 | 1 | 9 |  | TL
Marketing | New Brands |  | weinform.org personsearchers.com inmatelookup.net | Sales - H | UX 1.5 Platform 1.1 | 22 | 13 | 2 | 1 | 9 |  | TL
Product | ID Protection / SPY Features |  | Add ID Protection and SPY to Member site | ID / Spy will decrease cancels - L | Privacy Maxx contract | 22 | 13 | 2 | 1 | 9 |  | TL
Tech | Platform 1.1 |  | Change our code so it's difficult (but not impossible) to link our brands e.g. changing function names | Double serving can increase google sales 50% - M | Hire Back End Dev, UX2 | 21 | 12 | 2 | 1 | 9 |  | PP
Billing | Lower CB rates |  | Descriptor testing, IVR testing, increased CSR hours |  | CSR reporting | 21 | 12 | 1 | 2 | 9 |  | MC
CSR | Integrated CSR |  | New VOIP integrated with our CSR App and the creation of CSR reporting |  |  | 20 | 15 | 3 | 4 | 5 |  | MC
Product | SEO Site |  | Build out SEO Site with SEO data and SEO enhancements | SEO site will generate 10% more sales - M | Hire SEO Team - Mgr + 1 | 19 | 16 | 5 | 4 | 3 |  | TL
Product | InmateLookup.net |  | Clone PrisonPro.com. Add Inmate Data and Services to Member site / create IML as an Imate focused site | Inmate features will decrease cancels for 13% of our members - M | see what we learn from Inmate Hack | 19 | 15 | 5 | 3 | 4 |  | MC
Product | Property Data |  | Add strong Property Data to Member site | Prop Data will decrease cancels - L | n/a | 19 | 13 | 3 | 3 | 6 |  | MC
Product | Unclaimed Funds |  | Add Unclaimed Funds UX with scraped data to Membersite | Unclaimed Funds will decrease cancels - M | New Membersite | 19 | 12 | 2 | 3 | 7 |  | MC
Tech | Data Platform 2.1 |  | Change our data platform to support (phase 1) Supplemental Data, Pull on Demand | Improved data will lower cancel rates, lower refunds - M | Hire Data Team - Mgr + 1 | 18 | 16 | 5 | 5 | 2 |  | NP
Tech | Data Platform 2.2 |  | Change our data platform to support (phase 2) Manual Scraping, Scraping | Improved data will lower cancel rates, lower refunds - M | Hire Data Team - Mgr + 1 | 18 | 16 | 5 | 5 | 2 |  | NP
Tech | Data Platform 2.3 |  | Change our data platform to support (phase 3) Backup Data | Improved data will lower cancel rates, lower refunds - M | Hire Data Team - Mgr + 1 | 18 | 16 | 5 | 5 | 2 |  | NP
Product | SafeForKids.net |  | Clone KidsLiveSafe.com using Privacy Maxx and Core data https://prnt.sc/sxvmx3 | We can grow this mini vertical, which was successful as an Ad on our Membersite - M | Privacy Maxx contract | 18 | 14 | 4 | 4 | 4 |  | TL
Billing | Gateway |  | Replace Verifi with our own gateway (or ISO gateways?). Use initially for retries. Verifi is expensive https://prnt.sc/sxvexp | We can replicate Verifi's functionality relatively bug-free and renegotiate contract - M | Verifi contract | 17 | 15 | 5 | 5 | 2 | 0% | TL | Biggest risk is bugs, but will save us $6500/mo
CSR | CSR Redesign |  | CSR Admin redesign for multi branding | CSRs will be more productive, saving costs and refunds. We'll be able to create new tool for CSRs w/o Ops impact- H | n/a | 17 | 10 | 4 | 1 | 7 | 0% | MC
Marketing | Sales Site touch ups |  | https://docs.google.com/document/d/1n4KHDmhv5CtdLh1EfuyTlSiU2RQcTzvzus61eCzIMf8/edit Notification Page, SSI, CPCC, etc | This will increase CVR% and Retention Rate - L | n/a | 17 | 8 | 1 | 2 | 9 | 0% | TC | This was part of the Sales Site touch ups project (failure)
Tech | UXC CMS |  | Create a new UXC content management tool, replacing qa.admin.mc2data.com/admin | Current CMS is error-prone, not scalable - M | n/a | 17 | 8 | 2 | 1 | 9 |  | PP
Billing | Account Updater |  | Several vendors like QP or BLS | Updated cards and better recurring billing |  | 17 | 8 | 2 | 1 | 9 |  | TL
Product | Marketing Data |  | Add Marketing Data (e.g. for Lead Gen) as a supplement to our Core data | Marketing Data will improve our PDB, which will decrease cancels - L | Hire Data Team | 16 | 10 | 3 | 3 | 6 |  | TL
Marketing | Phone # on SUP | https://gitlab.mc2data.com/root/Dev/issues/372 | SMS needs phone # on the SUP step 1 Also benefits CSR for caller ID screening | SMS will increase sales 3% and not hurt CVR - M | n/a | 16 | 10 | 3 | 3 | 6 | 0% | TC | SMS biggest win, but need to test if phone collection will hurt CVR% first;
Billing | April 18 Visa |  | Toggle Web cancels for a specific MID | We need this capability to satisfy our ISO's - L | n/a | 16 | 6 | 1 | 1 | 10 |  | TL
Reports | Reports 2.0 |  | Rearchitect our reporting data so it's easier and faster for us to analyze data e.g. retention for DAR(r) | Faster reporting will make the company perform better - H | n/a | 14 | 8 | 3 | 3 | 6 |  | NP
Marketing | Native | https://gitlab.mc2data.com/root/Biz/issues/115 | Launch Native Ads, TV LPs with Env | Envyus will get us more traffic with Native - L | n/a | 14 | 6 | 1 | 3 | 8 | 0% | MC
Tech | Monitoring |  | Monitor our systems better to avoid slowdowns, downtime, problems with bugs | We have alot of problems - L | n/a | 14 | 6 | 2 | 2 | 8 |  | NP
Tech | Angular Universal Tech |  | Convert to a different version of Angular for faster loading our landing page. |  | n/a | 14 | 6 | 3 | 1 | 8 |  | PP | this will speed up the LP for slow phones, and the redirect
Category | Project | Priority | Benefit | Description | Reference |  | Who |  | Comments
MBMC | MC2 Data entanglements | P1 | MID separation | disconnect all companies from each other - see sunbiz.org |  |  | LC
HR | Hire developers | P1 | increased throughput |  |  |  | NP
Billing | CPSSI follow up | P2 | prioritize based on results; increase trans, rev (low...but would need to see perf first) | need to see how it's performing; copy and offer optimization | https://docs.google.com/spreadsheets/d/1DZjS7Tbuc__RFfwoh6Ml_HB3GSAeIyNW3o4Wg7uNcxE/edit#gid=592304673&range=B1 | https://prnt.sc/s1r9k6 | LC
UXC Config | LE RR's | P2 | sales | create separate Marriage/Divorce RR vs. Death RR |  |  | LC |  | increased priority
Product | Additional Resources | P2 | product value prop | Get links for Mini Reports | https://docs.google.com/spreadsheets/d/1wkgcpcrqqjjCJip4jtwYWtRg0eeXhf9z6coI1paABoM/edit#gid=132496499&range=A1 |  | All
Billing | Disclosure Testing | P3 | increase compliance, potentially MID capacity | combo in step 1, hybrid, upsell | https://docs.google.com/spreadsheets/d/1hUQtNsZVSttMFnyUVzESu53KaLqFwIzYgSZBv2o0zVg/edit#gid=2081971423&range=B1 | https://prnt.sc/s1u0jc | MC |  | rejected by QP but for the FTC, not for Visa
Corp Arch | WI/PsS/IL | P3 | sales, merch proc | build out brands with content | https://docs.google.com/spreadsheets/d/1hHB2qpstdjM1FJGHw-_CHpzYSII0SVMQ8Ct-vjdvwcU/edit#gid=1679836541&range=AE16 |  | LC
Reports | Conv Pixel | P3 | optimize ad copy in google | google Conv pixel values does not match retention perfectly |  |  | LC
Billing | casP | P4 | P/L | turn ON casP for affiliates. Alternative is to lower CPA for bad pubs (need to monitor perf). 15618, need to wait for Scrubber. |  |  | MC
Reports | Cal Retention | P4 | product | How many days do our customers stick around for? Used for understanding PMPM fees to data vendors |  |  | LaC
Sales | RR | P4 | split test cvr | challenger = campaign specific RRs |  |  | LC
Reports | Immediate Conv Pixel | P5 | tracking accuracy | Immediate campaigns in TROAS account do not track sales conversions perfectly |  |  | LC
Product | TV site | P5 | ??? | ??? |  |  | MC
Remarketing to use Angles

## Q4 2020 (hidden)
Theme: Focus on customer value, see if we can move retention, and increase operational efficiency
ID | Category | Project | Target | Actual | Description | Benefit - with probability | Dependency | Responsible | New Feature? | TC | PP | MC | MD | JR | PU | JS | TL | Done?
1 | Marketing | SUP Phone | 2020-11-15 |  | Collect phone number on SUP to be used in CSR and remarketing | Support operational efficiency -H Sales - M |  | PU | New Feature | PP: Dev; MC: CSR Training; JR: Remkting; PU: Product; TL: DBA
3 | Product | Unlim Social | 2020-11-15 |  | Get the ability to do unlimited social searches and images | More product value - H |  | TL | New Feature | PP: Dev; PU: Member; TL: Biz Dev
5 | Product | LN | 2020-11-15 |  | Get test agreement in place | Product value - M |  | TC | New Feature | TC: Biz Dev
6 | Compliance | Disc 1.2 | 2020-11-15 |  | Look at any remaining items for testing |  |  | TC | Testing | TC: Copy; TL: DBA
7 | PCI | Take over PCI | 2020-11-15 |  | Transfer PCI over to Jean |  |  | MC | Maintenance | MC: Training; TL: Trainer; Done?: Done
10 | Support | Prorated | 2020-11-15 |  | Test pro-rated refunds |  |  | MC | New Feature | MC: Policies/Training; TL: Support
12 | Marketing | tCPA profitable | 2020-11-15 |  | Modify tCPAs on any campaigns that are losing |  |  | JR | Maintenance | TC: Audit; JR: G Ads; Done?: Done
16 | Product | Sales Site 2/3 | 2020-11-15 |  | Launch Sales Site code with UX 2.0 and UX 3.0 |  |  | PU | New Feature | PP: Dev; PU: Product; TL: DBA; Done?: Done
18 | Biz Ops | Operationalize Sales 2 | 2020-11-15 |  | Launch the brands for Fluent |  | 12 | TL | New Feature | TC: Support; MC: CSR Training; TL: DBA/PM/MIDs/Mkting; Done?: Done
22 | Support | Refund App | 2020-11-15 |  | Launch refund app | Lower refunds - H |  | MC | New Feature | PP: Dev; MC: Policies/CSR Training; TL: Product; Done?: Done
27 | Biz Ops | Operationalize Sales 3 | 2020-11-20 |  | Launch the brands for EnvyUs |  | ID | TL | New Feature | TC: Support; MC: CSR Training; TL: DBA/PM/MIDs/Mkting; Done?: Done
2 | Marketing | Offline Conversions | 2020-12-01 |  | Optimize around retention instead of conversions |  |  | JR | New Feature | PP: Dev; JR: G Ads; PU: Product
8 | HR | Hire Growth Marketer | 2020-12-01 |  | Hire a growth marketer |  |  | TL | New Feature | bar: TC; TL
13 | Marketing | Test Bing | 2020-12-01 |  | Can we get Bing working? |  |  | JR | New Feature | TC: Support; JR: Campaigns; TL: Support
14 | Marketing | Push optimization | 2020-12-01 |  | Optimize push remarketing |  |  | JR | Maintenance | TC: Trainer; JR: Campaigns
19 | Product | Member 2.1 | 2020-12-01 |  | Get MVP Membersite 2.1 ready w/o all the new backend features | Product value - H |  | PU | New Feature |  | Dev | CSR Training | Design |  | Product | Advertising |  | Done
20 | Product | 2.1 Reverse Phone | 2020-12-01 |  | Get the membersite reverse phone funnel into the Member 2.1 experience | Product value - H | 19 | PU | New Feature | PP: Dev; MD: UX; PU: Product
15 | Marketing | SMS Remarketing | 2020-12-15 |  | Launch SMS remarketing with opt out functionality and also do not SMS signups. | Low cost sales - H | 1 | JR | New Feature | PP: Dev; JR: Campaigns; TL: Copy/DBA/Biz Dev
17 | Support | Action Recommender | 2020-12-15 |  | Launch rules to help standardize CSR business policies. | Standardized bus policies - H |  | MC | New Feature | PP: Dev; MC: Policies/CSR Training; TL: DBA
21 | Product | 2.2 Inmate | 2020-12-15 |  | Get the current inmate content onto all of our sites | Product value - ML | 15 | PU | New Feature | PP: Dev; MD: UX; PU: Product
23 | Billing | $29 Billing | 2020-12-15 |  | Try $29/mo to see if that materially helps retention | Retention - L |  | TL | Testing | TL: DBA
28 | Billing | CPCC 1.2 | 2020-12-15 |  | CPCC with good UX | Retention - M |  | TC | New Feature | TC: Support; MD: UX; PU: Product; TL: DBA
44 | Billing | RDR | 2020-12-15 |  | Launch RDR with Verifi (said it will be avail 12/11) |  |  | TL |  | Done?: Done
11 | Costs | Twilio Direct | 2021-01-01 |  | Use Twilio for call costs instead of through FC | Lower Call Costs - H |  | MC | New Feature | bar: MC
24 | Product | Test LN | 2021-01-01 |  | Test new data provider | Product value - M | 6 | PU | New Feature | PP: Dev; TL: PDB
25 | Product | Member 2.2 | 2021-01-01 |  | Launch membersite with all the backend features we orig intended | Product value - MH | 19 | PU | New Feature | PP: Dev; MD: UX; PU: Product; JS: Advertising
29 | Biz Dev | LN | 2021-01-01 |  | Do we do a deal with them? | Product value - M | 28 | TC | New Feature | TC: Support; TL: Biz Dev
4 | Marketing | Dating UXC |  |  | Customized content for Dating UXC |  |  | TL | Testing | MD: Copy; TL: DBA; Done?: Done
26 | HR | Hire Engineering Manager |  |  | Get an engineering manager that can help manage the devs | Operational efficiency - M |  | TL | New Feature | bar: PP; TL
30 | Product | Member 2.3 |  |  | Membersite with LN. This includes new ways to search incl property search | Product value - M |  | PU | New Feature | PP: Dev; MD: UX; PU: Product
31
32
33 | Billing | Upsells | [5 empty] | TL | New Feature | PP: Dev; MD: UX; PU: Product; JS: Offer Analysis; TL: Billing
34 | Support | CSR App 2.0 Bui/Buy | [5 empty] | TL | New Feature | PP: Dev; MC: Product; MD: UX; TL: Biz Dev
35 | Product | Unclaimed Funds | [5 empty] | TL | New Feature | PP: Dev; MD: UX; PU: Product; TL: Biz Dev
36 | Product | ID Protection | [6 empty] | New Feature | PP: Dev; MD: UX; PU: Product
37 | Product | SPY | [6 empty] | New Feature | PP: Dev; MC: Compliance; MD: UX; PU: Product; TL: Compliance
38 | Marketing | Reverse Phone Sales Site | [5 empty] | PU | New Feature | PP: Dev; MD: UX; PU: Product
39 | Product | Sales Site 4 | [5 empty] | PU | New Feature | PP: Dev; MD: UX; PU: Product
40 | Product | Sales Site 5 | [5 empty] | PU | New Feature | PP: Dev; MD: UX; PU: Product
41
42
43 | Product | UXC Management Tool |  |  | Prone to errors, hard to see current config, want to re-use content |  |  | TL
45
46
47
48
49
50
51
52
53
54
55
56

## Q1 2021 (hidden)
ID | Category | Project | Description | Benefit - with probability | Dependency | Responsible | PP | MC | MD | JR | PU | TL | Done? | Total Points | Impact | Dev Effort | Ops Effort | Effort (calc)
14 | Billing | $29 Billing | Try $29/mo to see if that materially helps retention | Retention - L |  | TL | [5 empty] | DBA | Yes | 30 | 20 | 1 | 1 | 10
7 | HR | Hire HR and Growth Marketer | Hiring |  |  | TL | [5 empty] | HR |  | 27 | 18 | 1 | 2 | 9
15 | Billing | CPCC 1.2 | CPCC with good UX | Retention - M |  | PU |  | CSR Support | UX |  | Product | DBA | Yes | 27 | 18 | 2 | 1 | 9
10 | Product | 2.1 Reverse Phone | Get the membersite reverse phone funnel into the Member 2.1 experience | Product value - H |  | PU | Dev |  | UX |  | Product |  | Yes | 26 | 18 | 2 | 2 | 8
18 | Product | Member 2.2 | Launch membersite with all the backend features we orig intended | Product value - MH |  | PU | Dev |  | UX |  | Product | Ads | Yes | 26 | 18 | 3 | 1 | 8
2 | Billing | Gateway | Move off current gateway | Cost savings - H |  | TL | Dev |  |  |  |  | Biz Dev |  | 25 | 20 | 5 | 2 | 5
11 | Marketing | SMS Remarketing | Launch SMS remarketing with opt out functionality and also do not SMS signups. | Low cost sales - H |  | JR | Dev | CSR Support |  | Campaigns | Product | Copy/DBA/Biz Dev | Yes | 25 | 20 | 4 | 3 | 5
13 | Product | 2.2 Inmate | Get the current inmate content onto all of our sites | Product value - ML |  | PU | Dev |  | UX |  | Product |  | Yes | 25 | 16 | 2 | 1 | 9
1 | Product | Unlim Social | Get the ability to do unlimited social searches and images | More product value - H |  | PU | Dev |  | UX |  | Member | Biz Dev |  | 24 | 15 | 2 | 1 | 9
8 | Marketing | Test Bing | Can we get Bing working? | Option to scale sales in future - M |  | JR |  |  |  | Campaigns |  | Support |  | 24 | 15 | 1 | 2 | 9
37 | Data | Data Platform 2.1 | Change our data platform to support (phase 1) Supplemental Data, Pull on Demand | Improved data will lower cancel rates, lower refunds - M |  | TL | Dev/IT | [6 empty] | 24 | 16 | 2 | 2 | 8
6 | Marketing | Offline Conversions | Optimize around retention instead of conversions | Retention - M |  | JR | Dev |  |  | G Ads | Product |  |  | 23 | 16 | 2 | 3 | 7
23 | Support | CSR App 2.0 Bui/Buy | Platform decision whether we modify CRM internally or migrate to a new one | Productivity - M |  | TL | Dev | Product | UX |  |  | Biz Dev | Yes | 23 | 15 | 3 | 1 | 8
43 | Support | VOIP Migration | VOIP Migration | Productivity - M |  | MC | Dev | Product
28 | Sales | UX 4 | New site to handle sales | Sales - M |  | PU | Dev |  | UX |  | Product |  |  | 23 | 16 | 2 | 3 | 7
29 | Sales | UX 5 | Usable for WIL double serving |  | Sales Site 1.1 | PU | Dev |  | UX |  | Product |  |  | 23 | 16 | 2 | 3 | 7
30 | Sales | Sales Site 1.1 (for UX5) | Allows us to double serve by changing UX5 backend so it looks different than our current site | Sales - M | UX 5 | PU | Dev |  |  |  | Product |  |  | 23 | 14 | 2 | 1 | 9
43 | Support | CRM Email and reporting | Email sending from the CSR App and all call reporting metrics in our d/b. Nice to have is a call connector to open up CRM on incoming call |  | CSR App 2.0 Bui/Buy | MC | Dev | Product | UX |  |  |  |  | 23 | 14 | 2 | 1 | 9
41 | Revenue | Account Updater | Update cards on file | Retention - M |  | PU | Dev |  |  |  | Product |  |  | 23 | 15 | 3 | 1 | 8
9 | Marketing | Push optimization | Optimize push remarketing | Low cost sales - ML |  | JR |  |  | Design | Campaigns |  |  |  | 22 | 13 | 1 | 2 | 9
12 | Support | Action Recommender | Launch rules to help standardize CSR business policies. | Standardized bus policies - H |  | MC | Dev | Policies/Training |  |  |  | DBA |  | 22 | 15 | 3 | 2 | 7
16 | Costs | Twilio Direct | Use Twilio for call costs instead of through FC | Lower Call Costs - H |  | MC |  | PM | [5 empty] | 22 | 13 | 1 | 2 | 9
19 | HR | Hire Engineering Manager | Get an engineering manager that can help manage the devs | Operational efficiency - M |  | TL | HR |  |  |  |  | HR |  | 22 | 13 | 2 | 1 | 9
20 | Product | Member 2.3 | Membersite with LN. This includes new ways to search incl property search | Product value - ML |  | PU | Dev |  | UX |  | Product |  |  | 22 | 14 | 3 | 1 | 8
21 | Revenue | Alternative Ad Networks | Market Research and Revenue from ads. Lead gen | Advertising - M |  | TL |  |  | UX |  | Product | Ads |  | 22 | 12 | 1 | 1 | 10
22 | Revenue | Upsells | Ancillary Revenue upselling existing products | Revenue or Transactions - M |  | PU | Dev | CSR Support | UX |  | Product | Billing |  | 22 | 16 | 4 | 2 | 6
41 | Revenue | Downsells | People trying to cancel that we are trying to save and keep on our service | Revenue or Transactions - M |  | PU | Dev | CSR Support | UX |  | Product | Billing
42 | Revenue | Welcome Back | People are expired and are re-logging back in to use the service. Re-selling the product | Revenue or Transactions - M |  | PU | Dev | CSR Support | UX |  | Product | Billing
24 | Product | Unclaimed Funds | Ability to search public records for lost and forgotten assets | Retention - M |  | PU | Dev | CSR Support | UX |  | Product | Biz Dev |  | 22 | 14 | 2 | 2 | 8
26 | Product | SPY | Ability to see if a person's information to other services were hacked in a data breach | Retention - M |  | TL | Dev | Compliance | UX |  | Product | Compliance |  | 22 | 14 | 2 | 2 | 8
36 | Product | Add strong property data to member site | Add ability to search by address | Retention - L |  | PU | Dev |  | UX |  | Product |  |  | 22 | 13 | 2 | 1 | 9
4 | Compliance | Disc 1.2 | Look at any remaining items for testing |  |  | TL | [5 empty] | DBA/Copy |  | 21 | 12 | 1 | 2 | 9
42 | Reporting | Reports 2.0 | Rearchitect our reporting data so it's easier and faster for us to analyze data e.g. retention for DAR(r) | Faster reporting will make the company perform better - H |  | TL | Dev |  |  |  |  | Product |  | 21 | 16 | 4 | 3 | 5
27 | Marketing | Reverse Phone Sales Site | New campaigns where input is phone instead of names |  |  | PU | Dev |  | UX |  | Product |  |  | 21 | 16 | 4 | 3 | 5
31 | Product | UXC Management Tool | Prone to errors, hard to see current config, want to re-use content |  |  | TL | Dev | Support | [5 empty] | 21 | 13 | 3 | 1 | 8
34 | Chargebacks | Fraud Protection | Protect against scrapers and true fraud |  |  | TL | Dev | [6 empty] | 21 | 12 | 1 | 2 | 9
38 | Data | Data Platform 2.2 | Change our data platform to support (phase 2) Manual Scraping, Scraping | Improved data will lower cancel rates, lower refunds - M |  | TL | Dev/IT |  |  |  |  | Product |  | 21 | 14 | 2 | 3 | 7
25 | Product | ID Protection | Identity theft protection as an additional feature for members | Retention - M |  | PU | Dev |  | UX |  | Product |  |  | 20 | 14 | 4 | 2 | 6
39 | Data | Data Platform 2.3 | Change our data platform to support (phase 3) Backup Data | Improved data will lower cancel rates, lower refunds - M |  | TL | Dev/IT |  |  |  |  | Product |  | 20 | 13 | 2 | 3 | 7
35 | Sales | SEO Site | Low cost sales |  |  | TL | Dev/IT |  | UX |  |  | Product |  | 19 | 16 | 5 | 4 | 3
3 | Product | LN | Get test agreement in place | Product value - M |  | TL | Dev |  |  |  |  | Biz Dev |  | 18 | 14 | 5 | 3 | 4
40 | Product | SafeForKids.net | Clone KidsLiveSafe.com using Privacy Maxx and Core data https://prnt.sc/sxvmx3 | We can grow this mini vertical, which was successful as an Ad on our Membersite - M |  | TL | Dev | CSR Support | UX |  |  | Product |  | 18 | 12 | 3 | 3 | 6

## Q1 2024
Project | Timeline | Main Project | Benefit with Probability | Main Biz Unit | Total Points | Impact | Profit | Risk | Strategic | Dev Effort | Ops Effort | Effort (calc) | Planned Date
Prime MID |  | Prime MID | Less Risk and Merchant Processing - M | Billing | 28 | 22 | 10 | 7 | 5 | 2 | 2 | 6 | 2025
UX 5.3 and Double Serve Trial | Oct | Double Serve | Increase footprint on search - M | Marketing | 26 | 21 | 12 | 7 | 2 | 1 | 4 | 5 | 2024
Alt Processing Networks (non-TSYS) |  | Prime MID | Statements showing low CB - H | Billing | 24 | 17 | 7 | 7 | 3 | 1 | 2 | 7 | 2024
CPCC 1.5 | Nov |  | Retention via better cards - M | Billing | 23 | 16 | 11 | 3 | 2 | 2 | 1 | 7 | 2024
Optimize push marketing | Dec |  | Diversify Marketing Channels/Risk - L | Marketing | 23 | 16 | 9 | 5 | 2 | 1 | 2 | 7 | 2026
Launch Fact Finders | Dec | FF | More product value - M-L | Product | 23 | 18 | 10 | 6 | 2 | 2 | 3 | 5 | 2024
Launch ID for everyone | Nov | ID | More product value - M-L | Product | 22 | 17 | 10 | 4 | 3 | 3 | 2 | 5 | 2024
Unclaimed Funds deal | Dec | UCF | More product value - M-L | Product | 22 | 14 | 8 | 5 | 1 | 1 | 1 | 8 | 2025
Launch Unclaimed Funds | Dec | UCF | More product value - M-L | Product | 22 | 15 | 8 | 5 | 2 | 2 | 1 | 7 | 2024
Data platform to support supplemental sources (scraped/manual) | Dec |  | More product value - L->M | Product | 22 | 16 | 7 | 5 | 4 | 2 | 2 | 6 | 2026
Data platform to support backup (core) sources | Jan |  | More product value - L->M | Product | 22 | 17 | 7 | 5 | 5 | 2 | 3 | 5 | 2026
Social | Jan | More Sales | Diversify Marketing Channels/Risk - L | Marketing | 22 | 16 | 10 | 4 | 2 | 1 | 3 | 6 | 2025
CSR 2.1 that supports FF | Dec | FF | More product value - M-L | Product | 21 | 14 | 8 | 5 | 1 | 2 | 1 | 7 | 2024
Immediate Billing | Jan |  | Increase footprint on search - M | Marketing | 21 | 16 | 10 | 5 | 1 | 2 | 3 | 5 | 2024
Improve SPY and add monitoring | Nov | SPY | More product value - M-L | Product | 21 | 15 | 10 | 3 | 2 | 2 | 2 | 6 | 2024
Optimize around retention - Google | Nov | Double Serve | More revenue - L | Marketing | 21 | 16 | 9 | 5 | 2 | 2 | 3 | 5 | 2024
UXC Management Tool | Feb |  | Lower config risk, inc speed of ops - L | Corp | 21 | 17 | 8 | 7 | 2 | 4 | 2 | 4 | 2026
Reporting 2.0 | Feb |  | More flexible reporting - M | Corp | 21 | 18 | 8 | 6 | 4 | 4 | 3 | 3 | 2026
Optimize Refund Rates | Dec |  | Lower risk for same or similar refunds - M-L | CSR | 21 | 14 | 6 | 6 | 2 | 1 | 2 | 7 | 2026
CB Importing and Reporting |  | Prime MID | Better visibility to risk - H | Billing | 20 | 16 | 8 | 5 | 3 | 4 | 2 | 4 | 2024
CRM Reporting | Oct | CSR Platform 2.0 | Better CSR operations/reporting H | CSR | 20 | 16 | 7 | 6 | 3 | 4 | 2 | 4 | 2025
Create competitor / third party accounts for DD | Dec | FF | More product value - M-L | Product | 20 | 13 | 7 | 5 | 1 | 1 | 2 | 7 | 2024
Ethoca |  | Prime MID | Less RIsk - M | Billing | 19 | 15 | 6 | 7 | 2 | 3 | 3 | 4 | 2024
FInish Gateway |  | Prime MID | Lower transaction costs - M | Billing | 19 | 16 | 10 | 4 | 2 | 5 | 2 | 3 | 2024
Call Remarketing |  | More Sales | More Sales - M-L | Marketing | 19 | 16 | 10 | 3 | 3 | 2 | 5 | 3 | 2025
Fact Finders | Nov | FF | More product value - M-L | CSR | 19 | 17 | 10 | 4 | 3 | 4 | 4 | 2 | 2024
New Marketing Partners | Dec | More Sales | Diversify Marketing Channels/Risk - M | Marketing | 19 | 16 | 10 | 4 | 2 | 2 | 5 | 3 | 2024
Hire Sys Admin | Feb |  | Stable servers - M-L | Dev | 19 | 12 | 6 | 5 | 1 | 2 | 1 | 7 | 2025
SEO | Mar |  | Diversify Marketing Channels/Risk - L | Marketing | 19 | 17 | 10 | 5 | 2 | 5 | 3 | 2 | 2025
Social Search | Nov |  | Ability to do a social search in the membersite and get a social mini report | [9 empty] | 2025
Email and property search | Nov |  | Ability to get email and property reports | [9 empty] | 2025

## Q2 2020 (hidden)
Category | Project | Gitlab | Description | Assumption - with probability | Value | Dev Effort | Ops Effort | Effort (calc) | Total Points | Prio | Status | Date | Responsible | Comments | Hide
Merch Proc | Lower Costs |  | Jetpay et al, after CPSSI lowers CB ratios | ISO's will lower rates with lower CB Ratios - M | 14 | 0 | 1 | 11 | 25 | VH | 80% | 2020-05-15 | MC | Need to wait for April statement, with lower CB ratio due to CPSSI. We pay ~$45K/mo so a 10% savings is $5K/mo | hide
Merch Proc | More MIDs |  | Get MIDs for PS, PS123, BC | ISO's will provide MIDs with LaC signature, new corp - H | 14 | 0 | 1 | 11 | 25 | VH | 80% | 2020-05-15 | Product | Will require a new entity. New oppty = CWAMS, BLS, STRONG
Growth | PS | https://gitlab.mc2data.com/root/Dev/issues/347#note_5150 | Launch new PS site in google (comprehensive) | We can acquire low CPA sales for a 2nd brand in google - M | 18 | 0 | 5 | 7 | 25 | VH | 100% | 2020-04-15 | Product, MC | Requires product, merchant proc, CSR, etc (lots of things). Need launch strategy. Names/PS? Immediate? Upper HHI demo? Do we try ROAS on this, which means we would need the S1.x pixel? https://docs.google.com/spreadsheets/d/1DZjS7Tbuc__RFfwoh6Ml_HB3GSAeIyNW3o4Wg7uNcxE/edit#gid=1101665376&range=A1 | hide
Merch Proc | Router |  | Ability to move traffic from brand to brand before signup | [11 empty] | hide
Marketing | New channels |  | Since google is shutting down LE, we need channels for LE kw's, possibly with TV. | We can generate LE traffic outside of google - L | 18 | 1 | 5 | 6 | 24 | VH | 0% | 2020-05-15 | MC | Very difficult. Try FB, Bing, Env, Fluent
Product | Membersite Mar 2020 |  | New Membersite (comprehensive) | A nicer design will reduce cancel rates - M | 18 | 5 | 3 | 4 | 22 | H | 20% | June 1 - 15 | MC, Product, Tech | design by Melissa, front end by new Korean dev, back end by IT. Need data providers like Ancestry.com
Billing | CPCC | https://gitlab.mc2data.com/root/Biz/issues/90 | Collect 2nd card for billing | Members will enter a new payment card after sign up - L | 15 | 3 | 3 | 6 | 21 | H | 0% | 2020-05-01 | Product, Tech | Spec = https://docs.google.com/document/d/1-WznWg-eXFoTluoOQ9nrTDvRAUEqO5O4mAlzc_WyMJo/edit | hide
Billing | CPSSI | https://gitlab.mc2data.com/root/Dev/issues/4 | Optimize trans adders beyond what we have now, and include 5-day trial | We can do trans adders very aggressively (wrong...only semi-aggressively with 4x $1 trans = SUP, SSI, 2x CPSSI) and not get caught - M | 10 | 1 | 1 | 10 | 20 | H | 100% | 2020-04-15 | Product | This is just for the incremental phase 2 work, 1/2 of which is spec'd in CPCC (casD part) | hide
Marketing | Scrubber |  | NEW | we know this works | 12 | 3 | 1 | 8 | 20 | H | 0% | 2020-04-30 | Product, Tech | A flexible way to scrub sales (via casD, casP, BIN, dial controlled by us). CasD already done since we don't trigger the pixel, and don't include in sales email report. Next would be the dial we control.
Marketing | New campaigns |  | Online dating, NAMES in google, Reverse Phone | There are keywords that we are not exposed to - L | 13 | 2 | 4 | 6 | 19 | M | 0% | 2020-06-15 | MC | Try ad customizers in google - https://support.google.com/google-ads/answer/6093368
Advertising | Sales Site Adv |  | Advertise on the Sales Site | We can advertise without hurting CVR - M | 10 | 1 | 3 | 8 | 18 | M | 0% | 2020-05-01 | Product, RC
CSR | CSR Redesign |  | CSR Admin redesign for multi branding | We'll be able to create new tool for CSRs w/o Ops impact- H | 11 | 4 | 1 | 7 | 18 | M | 0% | 2020-06-30 | Product
Marketing | Remkt One Signal | https://gitlab.mc2data.com/root/Dev/issues/372 | Personalization via integration, Land on RR/SUP, more campaigns, UXC config (show me how to modify preloader, single step SUP). Support outcomes if easy to do https://documentation.onesignal.com/docs/outcomes?utm_source=intercom&utm_medium=email&utm_content=button&utm_campaign=intercom-free-onboarding-outcomes | Personalization increases performance - L | 9 | 1 | 2 | 9 | 18 | M | 50% | 2020-06-30 | MC, Product, Tech | Consider using OS for emails. Flow can be seen here https://lionelchin710349.invisionapp.com/freehand/Backup-Files-qOU2ArUBA?v=HcpQlNW%2BeHqzbasz2RVINg%3D%3D&linkshare=urlcopied
Marketing | Remkt SMS | https://gitlab.mc2data.com/root/Dev/issues/372 | SMS needs phone # | SMS will work and not hurt CVR - M | 12 | 3 | 3 | 6 | 18 | M | 0% | 2020-06-30 | MC, Product, Tech | SMS biggest win, but need to test if phone collection will hurt CVR% first;
Marketing | Affiliate optimization | https://gitlab.mc2data.com/root/Dev/issues/383 | Track fraud, retention by Pub | Envyus affiliates will send us bad traffic - L | 10 | 2 | 3 | 7 | 17 | L | 0% | 2020-06-15 | Product, Tech | UXC/UXL for affiliates
Marketing | Notification Page |  | Notification Page that Rick created | This will increase CVR% and Retention Rate - L | 8 | 1 | 2 | 9 | 17 | L | 0% | 2020-06-30 | Product | This was part of the Sales Site touch ups project (failure)
Billing | Indicators Upsell |  | Sell PS report for $0.23, then upsell ala carte items | Customers will purchase upsells ala carte - L | 10 | 3 | 2 | 7 | 17 | L | 0% | TBD
Marketing | Native | https://gitlab.mc2data.com/root/Biz/issues/115 | Launch Native Ads, TV LPs with Env | Envyus will get us more traffic with Native - L | 8 | 1 | 3 | 8 | 16 | VL | 0% | 2020-06-30 | MC
Billing | Gateway |  | Replace Verifi with our own gateway | We can replicate Verifi's functionality relatively bug-free - M | 14 | 5 | 5 | 2 | 16 | VL | 0% | TBD | Tech, Product | Biggest risk is bugs, but will save us $6500/mo
Misc | Misc |  | SEO UXC, Domain mgmt, Logos | We can get these things done in our free time | 5 | 0 | 2 | 10 | 15 | VL | 100% | TBD | Product, MC | These tasks generally don't require Dev work | hide
Web cancels ON for a MID, retention for DAR(r), alerts/monitoring
Product | Property Data |  | NEW |  | 12 | 3 | 3 | 6 | 18 | M
Product | Leads Data |  | NEW |  | 12 | 3 | 3 | 6 | 18 | M
Tech | angular universal tech |  | NEW | [10 empty] | this will speed up the LP for slow phones, and the redirect
Category | Project | Priority | Benefit | Description | Reference |  | Who |  | Comments
Billing | Retries | P1 | increase revenue, lower Merch Proc costs. | Optimize retries for cascades (less attempts) | https://docs.google.com/spreadsheets/d/1hHB2qpstdjM1FJGHw-_CHpzYSII0SVMQ8Ct-vjdvwcU/edit#gid=1146213481 |  | LC | [7 empty] | hide
Sales | TV -> PS123 | P1 | Merch Proc capacity | move PS sales to PS123 (to free up MP cap space) |  |  | LC |  | this seems to perform worse -- makes no sense | [5 empty] | hide
Billing | CPCC | P1 | LTV | QA and configure CPCC |  |  | LC |  | does this need UX? None needed for launch. Target this build. | [5 empty] | hide
MBMC | MC2 Data entanglements | P1 | MID separation | disconnect all companies from each other - see sunbiz.org |  |  | LC
Billing | AVS | P1 | lower costs (Merch Proc) | turn OFF AVS at Verifi. only for BUSA? if so, will be lower priority (P3) |  |  | LC | [7 empty] | hide
HR | Melissa, Lisa | P1 | increased throughput | onboard Melissa, Lisa |  |  | LaC |  | in progress | [5 empty] | hide
Marketing | Similar Web | P1 | get competitive info | 1 day left on the trial |  |  | LC | [7 empty] | hide
HR | Hire developers | P1 | increased throughput |  |  |  | NP
Billing | CPSSI follow up | P2 | prioritize based on results; increase trans, rev (low...but would need to see perf first) | need to see how it's performing; copy and offer optimization | https://docs.google.com/spreadsheets/d/1DZjS7Tbuc__RFfwoh6Ml_HB3GSAeIyNW3o4Wg7uNcxE/edit#gid=592304673&range=B1 | https://prnt.sc/s1r9k6 | LC
UXC Config | LE RR's | P2 | sales | create separate Marriage/Divorce RR vs. Death RR |  |  | LC |  | increased priority
Sales | New Logos | P2 | help BC sales | BC, PS123 logos from Melissa added to site, emails, OneSignal |  |  |  |  | Target this build | [5 empty] | hide
Sales / Reports | Billing Failure | P2 | CPA | weekend problem w/ Envyus getting casD, gateway passthru sales. Need to fix monitoring, attribution, tableau report incorrect |  |  |  |  | stories filed | [5 empty] | hide
Product | Additional Resources | P2 | product value prop | Get links for Mini Reports | https://docs.google.com/spreadsheets/d/1wkgcpcrqqjjCJip4jtwYWtRg0eeXhf9z6coI1paABoM/edit#gid=132496499&range=A1 |  | All
Product | ID Protect | P2 | product value prop | explore licensing ID Protect from PrivacyMaxx (raised priority b/c it's so interesting) |  |  | MC | [7 empty] | hide
UXC (all) | Remarketing UXC's | P2 | sales | no loader, RR, single step SUP w/ discount modal, blue box |  |  | LC |  | also need to double-check set up | [5 empty] | hide
Reports | Affiliate reporting | P2 | P/L | track LTV for affiliates (regular vs casD) |  |  | MC | [7 empty] | hide
Sales | blue price box | P3 | split test cvr | challenger = SUP step1 w/ discount modal + step 2 w/ blue price box |  |  | MC |  | split testing now | [5 empty] | hide
Billing | Disclosure Testing | P3 | increase compliance, potentially MID capacity | combo in step 1, hybrid, upsell | https://docs.google.com/spreadsheets/d/1hUQtNsZVSttMFnyUVzESu53KaLqFwIzYgSZBv2o0zVg/edit#gid=2081971423&range=B1 | https://prnt.sc/s1u0jc | MC |  | rejected by QP but for the FTC, not for Visa
Corp Arch | WI/PsS/IL | P3 | sales, merch proc | build out brands with content | https://docs.google.com/spreadsheets/d/1hHB2qpstdjM1FJGHw-_CHpzYSII0SVMQ8Ct-vjdvwcU/edit#gid=1679836541&range=AE16 |  | LC
Reports | Conv Pixel | P3 | optimize ad copy in google | google Conv pixel values does not match retention perfectly |  |  | LC
Billing | casP | P4 | P/L | turn ON casP for affiliates. Alternative is to lower CPA for bad pubs (need to monitor perf). 15618, need to wait for Scrubber. |  |  | MC
Reports | Cal Retention | P4 | product | How many days do our customers stick around for? Used for understanding PMPM fees to data vendors |  |  | LaC
Sales | RR | P4 | split test cvr | challenger = campaign specific RRs |  |  | LC
Reports | Immediate Conv Pixel | P5 | tracking accuracy | Immediate campaigns in TROAS account do not track sales conversions perfectly |  |  | LC
Product | TV site | P5 | ??? | ??? |  |  | MC
Billing | CPSSI | n/a | 5-day trial, $1 SUP + $1 SSI + 2x $1 CP | Monitor very closely |  |  | LC | [7 empty] | hide